## Instructions
Cement & Aggregates Inventory Monitoring — Housing Projects
Tracks cement, sand, gravel (3/4" and 3/8") and concrete admixture per housing site: current stock, consumption from the m3 of concrete produced (via mix design), new deliveries, critical-stock alerts, a daily-to-monthly consumption forecast and a visual dashboard with % of capacity and days remaining.
SAMPLE DATA: this copy is filled with illustrative figures for 8 sites (count date 1-Oct-2026, daily logs to 31-Oct-2026) so you can see how it works. The quantities are made up. Use the blank 'Cement and Aggregates Inventory.xlsx' for real data.
HOW TO USE
1. Settings — check the As-of Date (=TODAY() by default), working days per week/month, the materials (unit, supplier lead time, safety stock), the site list and (optional) non-working holidays.
2. Mix Design — enter your approved mix design: quantity of each material per 1 m3 of concrete (cement in bags, aggregates in m3, admixture in litres), plus the allowance (waste) %.
3. Current Inventory (1) — one row per site and material: count date, beginning balance (physical count) and maximum storage capacity.
4. Consumption Log (2) — every day, record the concrete produced: date, site, mix code and m3. The cement, sand, gravel and admixture used are calculated from the mix design and deducted from stock.
5. Deliveries (3) — record every delivery receipt as 'Received' (added to stock on its date). Also record purchase orders not yet delivered as 'Scheduled' with the expected date: they are not added to stock, but the monitor and the forecast count them as on order.
6. Production Plan (5) — declare the planned m3 per working day for each site and mix. This drives the daily usage, days remaining, critical dates and the monthly forecast.
7. Stock Monitor (4), Forecast (5) and Dashboard (6) are automatic. On the Dashboard, pick a site (or All Sites) in the yellow cell.
Dashboard silo, bins & tank: the cement silo, the 3 aggregate bins and the admixture tank fill up to their % of max storage capacity (bands of 5 %). '– – critical level – –' marks the stock needed for the supplier lead time and '– – reorder level – –' the stock for lead time + safety stock; the badge under each vessel is its status.
COLOUR LEGEND
Yellow cells = type your data here
Grey cells = calculated automatically — do not type over these
Light grey / italic row under each header = example showing the format — it is not counted
Check columns show ⚠ when something needs attention (missing date, unknown code, duplicate row, scheduled delivery date already passed, ...).
HOW CURRENT STOCK IS CALCULATED
Current Stock = Beginning Balance (physical count) + Deliveries Received − Consumption, counting transactions dated from the Count Date up to and including the As-of Date.
Consumption = m3 produced × mix design quantity per m3 × (1 + allowance %).
The physical count is taken at the START of the count date (before that day's deliveries and production).
Recount regularly (weekly or monthly): type the new count date and balance in Current Inventory. Older log rows then stop affecting the balance — there is no need to delete them.
CRITICAL-STOCK MONITORING (Stock Monitor and Dashboard)
Daily usage = declared m3/day (Production Plan) × mix design. If no plan is declared for a site, the actual average of the last 7 days (per working day) is used.
Days Remaining = stock on hand ÷ daily usage, in working days. Stock-out On = the working day the stock on hand runs out if nothing more arrives (non-working weekdays and holidays in Settings are skipped).
Planning Cover = days of usage covered by stock on hand plus deliveries already on order (Scheduled, or Received with a future date) — counted only when a delivery arrives on or before the stock-out day.
OK — planning cover is above lead time + safety stock.
REORDER — planning cover ≤ lead time + safety stock: place an order now.
CRITICAL — planning cover ≤ supplier lead time: stock will run out before a normal delivery can arrive (or the next delivery is due after the stock-out). Expedite.
OUT OF STOCK — stock on hand is zero or negative (negative also means a delivery or a recount is missing).
Reorder By = last working day to place the order before the planning cover falls to lead time + safety stock. Critical On = the working day the cover falls to the lead time. 'NOW' = already reached.
Suggested Order Qty = quantity that refills storage to its maximum capacity when the order arrives (after the usage during the lead time and counting what is already on order).
Dashboard 'All Sites' view: stock, capacity and usage are totals; dates are the earliest site; the status is the worst site. The All-Sites table shows each site and material separately.
FORECAST (Production Plan → Forecast)
Daily usage × working days per week = weekly; × working days per month = generic monthly requirement.
6 forecast periods: period 1 runs from the day after the As-of Date to month-end, then 5 calendar months. Each period uses its actual number of working days.
Still to Order = what must be delivered in each period, beyond the scheduled deliveries, so the period closes at the reorder level (lead time + safety stock of usage). It is the monthly procurement forecast.
Runs Out (no new orders) = first period in which stock on hand plus scheduled deliveries is used up.
ASSUMPTIONS (change them in Settings / Mix Design)
Mix design defaults are typical Philippine volumetric proportions per m3 with 40 kg cement bags, 0.50 m3 sand and 1.00 m3 gravel: Class AA (1:1.5:3) = 12 bags, Class A (1:2:4) = 9 bags, Class C (1:3:6) = 6 bags (as tabulated in common estimating references, e.g. M. Fajardo, Simplified Construction Estimate). Replace them with your approved, lab-tested mix design.
Admixture default dosage: 4.0 L/m3 for the precast mixes and 2.5 L/m3 for footings (typical superplasticizer / water-reducer range); none for lean concrete. Use the supplier's recommended dosage from your trial mixes.
Allowance 3% (precast) / 5% (cast in place), lead time 3 working days for cement, 2 for aggregates and 5 for admixture, safety stock 2 working days (3 for admixture), 6 working days per week (Sunday off) and 26 per month are starting assumptions. No holidays are entered by default, which is the conservative choice.
CAPACITY
Room for 100 site/material rows, 2,000 consumption rows, 1,000 deliveries, 80 plan rows, 20 mix designs and 20 sites. To extend a log, insert rows ABOVE its last row (the named ranges then grow) and copy the grey formula cells down.

## Dashboard
6 · Inventory Dashboard — Cement, Aggregates & Admixture | [7 empty] | SAMPLE DATA — illustrative figures only
As of Saturday, 31 October 2026 · Days are working days (6 per week) · Pick a site in the yellow cell
CHART DATA & HELPERS (automatic — do not edit)
Site / Project: | All Sites |  |  |  | Worst item status: | OUT OF STOCK |  | Critical / out: | 4 | To reorder: | 4 |  |  | Site criteria | *
Cement (bags) | Sand (m3) |  | Gravel 3/4" (m3) |  | Gravel 3/8" (m3) |  | Admixture (L) |  | Planned Production (concrete)
4.2614 | 5.9382 |  | 9.6409 |  | 6.0939 |  | 5.3526 |  | 141
Earliest out ≈ Mon 02-Nov | OUT OF STOCK now |  | Earliest out ≈ Sat 07-Nov |  | Earliest out ≈ Thu 05-Nov |  | Earliest out ≈ Mon 02-Nov |  | ≈ 3,666 m3 per month (26 working days)
7,288 bags · 37% full | 432 m3 · 49% full |  | 180 m3 · 64% full |  | 772 m3 · 52% full |  | 3,009 L · 41% full |  | Actual, last 7 days: 127.1 m3/day
CRITICAL | OUT OF STOCK |  | OK |  | REORDER |  | CRITICAL |  | PLAN DECLARED
Material | Unit | Current Stock | Max Capacity | % of Capacity | Use / Day | Days Remaining | On Order | Reorder By | Critical On | Stock-out On | Status | Sites Critical / Out | Suggested Order Qty | Code | Lead (days) | Safety (days) | Reorder level (lead + safety) | Critical level (lead time) | Days remaining (on hand) | % of capacity | Earliest reorder | Earliest critical | Earliest stock-out | Silo/bin fill (of 20 bands) | Critical mark (band) | Reorder mark (band)
Cement | bags | 7288.195 | 19750 | 36.9% | 1710.27 | 4.2614 | 4750 | NOW | NOW | 2026-11-02 | CRITICAL | 2 | 6809 | CEM | 3 | 2 | 5 | 3 | 4.2614 | 36.9% | 46326 | 46326 | 46328 | 7 | 5 | 9
Sand | m3 | 431.7365 | 888 | 48.62% | 72.705 | 5.9382 | 128 | NOW | NOW | OUT | OUT OF STOCK | 1 | 82 | SAND | 2 | 2 | 4 | 2 | 5.9382 | 48.62% | 46326 | 46326 | 46326 | 10 | 3 | 7
Gravel 3/4" | m3 | 180.478 | 284 | 63.55% | 18.72 | 9.6409 | 32 | 2026-11-04 | 2026-11-07 | 2026-11-07 | OK | 0 | 0 | G34 | 2 | 2 | 4 | 2 | 9.6409 | 63.55% | 46330 | 46333 | 46333 | 13 | 3 | 5
Gravel 3/8" | m3 | 772.032 | 1478 | 52.23% | 126.69 | 6.0939 | 112 | NOW | 2026-11-03 | 2026-11-05 | REORDER | 0 | 254 | G38 | 2 | 2 | 4 | 2 | 6.0939 | 52.23% | 46326 | 46329 | 46331 | 10 | 3 | 7
Admixture | L | 3009.3175 | 7400 | 40.67% | 562.215 | 5.3526 | 1800 | NOW | NOW | 2026-11-02 | CRITICAL | 1 | 2045 | ADM | 5 | 3 | 8 | 5 | 5.3526 | 40.67% | 46326 | 46326 | 46328 | 8 | 8 | 12
Days Remaining = stock on hand ÷ use per day (working days). Status, Reorder By and Critical On also count scheduled deliveries that arrive before the stock-out. All Sites: totals, the earliest date and the worst status across sites.
STORAGE LEVELS — CEMENT SILO, AGGREGATE BINS & ADMIXTURE TANK (all sites combined) · fill = stock on hand ÷ max storage capacity
AGGREGATE BINS
100% —
75% —
64%
– – reorder level – –
50% — |  |  |  | 49% |  |  |  | 52%
– – reorder level – –
– – critical level – –
| 37% |  |  | – – reorder level – – |  |  |  | – – reorder level – –
25% — | – – critical level – – |  |  |  |  | – – reorder level – –
|  |  |  | – – critical level – – |  | – – critical level – – |  | – – critical level – –
0% —
| CEMENT SILO |  |  | SAND BIN |  | GRAVEL 3/4" BIN |  | GRAVEL 3/8" BIN |  |  | ADMIXTURE TANK
| 37% full |  |  | 49% full |  | 64% full |  | 52% full |  |  | 41% full
| 7,288 / 19,750 bags |  |  | 432 / 888 m3 |  | 180 / 284 m3 |  | 772 / 1,478 m3 |  |  | 3,009 / 7,400 L
| 4.3 days left |  |  | 5.9 days left |  | 9.6 days left |  | 6.1 days left |  |  | 5.4 days left
| CRITICAL |  |  | OUT OF STOCK |  | OK |  | REORDER |  |  | CRITICAL
How to read: coloured fill = stock on hand ÷ max storage capacity (5 % bands) · – – critical level – – = usage during the supplier lead time · – – reorder level – – = lead time + safety stock · badge = status (counts scheduled deliveries) · All Sites = combined stock and capacity
ALL SITES — DAYS REMAINING (working days, colour = status) AND % OF CAPACITY
Site / Project | Cement days left | Sand days left | Gravel 3/4" days left | Gravel 3/8" days left | Admixture days left | Cement % full | Sand % full | Gravel 3/4" % full | Gravel 3/8" % full | Admixture % full | Worst Status | Lowest Days Left | Stock-out ≈
Batulao Parkhomes | 5.9678 | 8.0628 | 13.0113 | 8.1665 | 5.7123 | 48.33% | 65.75% | 83.76% | 67.29% | 44.72% | REORDER | 5.7123 | 2026-11-07
Calauan (Alora+Amani) | 4.2704 | 4.7686 | 5.4262 | 4.8232 | 6.3294 | 38.9% | 45.74% | 37.98% | 47.52% | 53.35% | REORDER | 4.2704 | 2026-11-06
Gentri | 8.4288 | 3.5745 |  | 5.6133 | 7.458 | 74.41% | 26.3% |  | 44.47% | 51.21% | REORDER | 3.5745 | 2026-11-05
Naic | 0.29983 | 5.5138 | 9.5563 | 6.8736 | 4.7721 | 2.839% | 42.59% | 73.82% | 57.4% | 44.24% | CRITICAL | 0.29983 | 2026-11-02
The Cove Lipa | 7.6232 | 7.2681 | 7.981 | 3.1862 | 0.86933 | 67.78% | 69.22% | 34.92% | 25.79% | 7.163% | CRITICAL | 0.86933 | 2026-11-02
Sights Bay | 5.055 | 8.1833 |  | 7.9406 | 8.4261 | 37.49% | 72.25% |  | 75.5% | 59.51% | OK | 5.055 | 2026-11-07
Tayabas | 6.5384 | 0 |  | 13.6042 | 16.5168 | 32.33% | 0% |  | 87.58% | 34.02% | OUT OF STOCK | 0 | OUT
Batulao Impression | 1.7899 | 4.8487 | 13.227 | 5.5294 | 5.0792 | 16.27% | 39.45% | 86.8% | 50.62% | 34.57% | CRITICAL | 1.7899 | 2026-11-03
DAYS REMAINING vs REORDER & CRITICAL LEVELS · ACTUAL CONCRETE PRODUCTION, LAST 14 DAYS (selected site)
[14 empty] | Date | Actual m3 | Planned m3/day | Label
[14 empty] | 2026-10-18 | 0 | 141 | Sun 18
[14 empty] | 2026-10-19 | 135.9 | 141 | Mon 19
[14 empty] | 2026-10-20 | 141.9 | 141 | Tue 20
[14 empty] | 2026-10-21 | 116.3 | 141 | Wed 21
[14 empty] | 2026-10-22 | 123.4 | 141 | Thu 22
[14 empty] | 2026-10-23 | 141.4 | 141 | Fri 23
[14 empty] | 2026-10-24 | 129.2 | 141 | Sat 24
[14 empty] | 2026-10-25 | 0 | 141 | Sun 25
[14 empty] | 2026-10-26 | 138.3 | 141 | Mon 26
[14 empty] | 2026-10-27 | 116.5 | 141 | Tue 27
[14 empty] | 2026-10-28 | 128.4 | 141 | Wed 28
[14 empty] | 2026-10-29 | 121.2 | 141 | Thu 29
[14 empty] | 2026-10-30 | 129.1 | 141 | Fri 30
[14 empty] | 2026-10-31 | 129.1 | 141 | Sat 31
6-MONTH FORECAST — selected site (declared m3/day × mix design × working days per month)
Forecast consumption | Unit | Nov 2026 25 working days | Dec 2026 27 working days | Jan 2027 26 working days | Feb 2027 24 working days | Mar 2027 27 working days | Apr 2027 26 working days | 6-Period Total
Concrete (m3) | m3 | 3525 | 3807 | 3666 | 3384 | 3807 | 3666 | 21855 | [6 empty] | Concrete (m3)
Cement | bags | 42756.75 | 46177.29 | 44467.02 | 41046.48 | 46177.29 | 44467.02 | 265091.85 | [6 empty] | Cement use (bags)
Sand | m3 | 1817.625 | 1963.035 | 1890.33 | 1744.92 | 1963.035 | 1890.33 | 11269.275 | [6 empty] | Sand use (m3)
Gravel 3/4" | m3 | 468 | 505.44 | 486.72 | 449.28 | 505.44 | 486.72 | 2901.6 | [6 empty] | Gravel 3/4" use (m3)
Gravel 3/8" | m3 | 3167.25 | 3420.63 | 3293.94 | 3040.56 | 3420.63 | 3293.94 | 19636.95 | [6 empty] | Gravel 3/8" use (m3)
Admixture | L | 14055.375 | 15179.805 | 14617.59 | 13493.16 | 15179.805 | 14617.59 | 87143.325 | [6 empty] | Admixture use (L)
Scheduled deliveries | Unit | Nov 2026 | Dec 2026 | Jan 2027 | Feb 2027 | Mar 2027 | Apr 2027 | 6-Period Total
Cement | bags | 4750 | 0 | 0 | 0 | 0 | 0 | 4750
Sand | m3 | 128 | 0 | 0 | 0 | 0 | 0 | 128
Gravel 3/4" | m3 | 32 | 0 | 0 | 0 | 0 | 0 | 32
Gravel 3/8" | m3 | 112 | 0 | 0 | 0 | 0 | 0 | 112
Admixture | L | 1800 | 0 | 0 | 0 | 0 | 0 | 1800
Still to order (keeps the reorder level) | Unit | Nov 2026 | Dec 2026 | Jan 2027 | Feb 2027 | Mar 2027 | Apr 2027 | 6-Period Total
Cement | bags | 39269.905 | 46177.29 | 44467.02 | 41046.48 | 46177.29 | 44467.02 | 261605.005 | [6 empty] | Still to order (bags)
Sand | m3 | 1548.7085 | 1963.035 | 1890.33 | 1744.92 | 1963.035 | 1890.33 | 11000.3585 | [6 empty] | Still to order (m3)
Gravel 3/4" | m3 | 330.402 | 505.44 | 486.72 | 449.28 | 505.44 | 486.72 | 2764.002 | [6 empty] | Still to order (m3)
Gravel 3/8" | m3 | 2789.978 | 3420.63 | 3293.94 | 3040.56 | 3420.63 | 3293.94 | 19259.678 | [6 empty] | Still to order (m3)
Admixture | L | 13743.7775 | 15179.805 | 14617.59 | 13493.16 | 15179.805 | 14617.59 | 86831.7275 | [6 empty] | Still to order (L)
Still to order = forecast use − scheduled deliveries − stock above the reorder level, per period, so that each period closes at the reorder level (lead time + safety stock of usage). Details per site: Forecast sheet.
FORECAST VISUALS — selected site
Formulas:
Stock-out On = IF([Earliest stock-out]>=1000000000,"",IF([Earliest stock-out]<=AsOfDate,"OUT",[Earliest stock-out]))
Reorder By = IF([Earliest reorder]>=1000000000,"",IF([Earliest reorder]<=AsOfDate,"NOW",[Earliest reorder]))
Critical On = IF([Earliest critical]>=1000000000,"",IF([Earliest critical]<=AsOfDate,"NOW",[Earliest critical]))
Suggested Order Qty = IF([Sites Critical / Out]="","",IF([Sites Critical / Out]<=0,"OUT",WORKDAY.INTL(AsOfDate,ROUNDUP([Sites Critical / Out],0),WeekendMask,Holidays)))
Code = [Code, row above]+1

## Current Inventory
1 · Current Inventory — Stock on Hand per Site
One row per site and material: physical count (beginning balance), count date and storage capacity. Deliveries and consumption from the count date up to the As-of Date are applied automatically.
Stock as of 31 Oct 2026 (As-of Date is set in Settings)
Site / Project | Material Code | Material | Unit | Count Date | Beginning Balance (physical count) | Max Storage Capacity | Deliveries Received (+) | Consumption (−) | Current Stock | % of Capacity | Check | Remarks
Example Site | CEM | Cement | bags | 2026-10-01 | 1500 | 3000 | (auto) | (auto) | (auto) | (auto) |  | Example row — shows the format, not counted
Batulao Parkhomes | CEM | Cement | bags | 2026-10-01 | 2130 | 2900 | 5250 | 5978.532 | 1401.468 | 48.33% | OK | Opening count (sample)
Batulao Parkhomes | SAND | Sand | m3 | 2026-10-01 | 72 | 120 | 256 | 249.1055 | 78.8945 | 65.75% | OK | Opening count (sample)
Batulao Parkhomes | G34 | Gravel 3/4" | m3 | 2026-10-01 | 23 | 48 | 96 | 78.795 | 40.205 | 83.76% | OK | Opening count (sample)
Batulao Parkhomes | G38 | Gravel 3/8" | m3 | 2026-10-01 | 122 | 200 | 432 | 419.416 | 134.584 | 67.29% | OK | Opening count (sample)
Batulao Parkhomes | ADM | Admixture | L | 2026-10-01 | 640 | 1000 | 1800 | 1992.844 | 447.156 | 44.72% | OK | Opening count (sample)
Calauan (Alora+Amani) | CEM | Cement | bags | 2026-10-01 | 2070 | 3400 | 7000 | 7747.362 | 1322.638 | 38.9% | OK | Opening count (sample)
Calauan (Alora+Amani) | SAND | Sand | m3 | 2026-10-01 | 80 | 140 | 320 | 335.958 | 64.042 | 45.74% | OK | Opening count (sample)
Calauan (Alora+Amani) | G34 | Gravel 3/4" | m3 | 2026-10-01 | 32 | 60 | 96 | 105.21 | 22.79 | 37.98% | OK | Opening count (sample)
Calauan (Alora+Amani) | G38 | Gravel 3/8" | m3 | 2026-10-01 | 164 | 230 | 512 | 566.706 | 109.294 | 47.52% | OK | Opening count (sample)
Calauan (Alora+Amani) | ADM | Admixture | L | 2026-10-01 | 770 | 1200 | 2400 | 2529.849 | 640.151 | 53.35% | OK | Opening count (sample)
Gentri | CEM | Cement | bags | 2026-10-01 | 960 | 1400 | 3000 | 2918.196 | 1041.804 | 74.41% | OK | Opening count (sample)
Gentri | SAND | Sand | m3 | 2026-10-01 | 44 | 70 | 96 | 121.5915 | 18.4085 | 26.3% | OK | Opening count (sample)
Gentri | G38 | Gravel 3/8" | m3 | 2026-10-01 | 77 | 130 | 224 | 243.183 | 57.817 | 44.47% | OK | Opening count (sample)
Gentri | ADM | Admixture | L | 2026-10-01 | 280 | 600 | 1000 | 972.732 | 307.268 | 51.21% | OK | Opening count (sample)
Naic | CEM | Cement | bags | 2026-10-01 | 3360 | 4700 | 8000 | 11226.588 | 133.412 | 2.839% | OK | Opening count (sample)
Naic | SAND | Sand | m3 | 2026-10-01 | 154 | 240 | 416 | 467.7745 | 102.2255 | 42.59% | OK | Opening count (sample)
Naic | G34 | Gravel 3/4" | m3 | 2026-10-01 | 55 | 80 | 160 | 155.942 | 59.058 | 73.82% | OK | Opening count (sample)
Naic | G38 | Gravel 3/8" | m3 | 2026-10-01 | 192 | 370 | 800 | 779.607 | 212.393 | 57.4% | OK | Opening count (sample)
Naic | ADM | Admixture | L | 2026-10-01 | 1050 | 1600 | 3400 | 3742.196 | 707.804 | 44.24% | OK | Opening count (sample)
The Cove Lipa | CEM | Cement | bags | 2026-10-01 | 2110 | 3200 | 7000 | 6941.052 | 2168.948 | 67.78% | OK | Opening count (sample)
The Cove Lipa | SAND | Sand | m3 | 2026-10-01 | 72 | 130 | 320 | 302.0205 | 89.9795 | 69.22% | OK | Opening count (sample)
The Cove Lipa | G34 | Gravel 3/4" | m3 | 2026-10-01 | 36 | 48 | 32 | 51.24 | 16.76 | 34.92% | OK | Opening count (sample)
The Cove Lipa | G38 | Gravel 3/8" | m3 | 2026-10-01 | 145 | 280 | 480 | 552.801 | 72.199 | 25.79% | OK | Opening count (sample)
The Cove Lipa | ADM | Admixture | L | 2026-10-01 | 690 | 1100 | 1600 | 2211.204 | 78.796 | 7.163% | OK | Opening count (sample)
Sights Bay | CEM | Cement | bags | 2026-10-01 | 1480 | 2000 | 3000 | 3730.248 | 749.752 | 37.49% | OK | Opening count (sample)
Sights Bay | SAND | Sand | m3 | 2026-10-01 | 46 | 70 | 160 | 155.427 | 50.573 | 72.25% | OK | Opening count (sample)
Sights Bay | G38 | Gravel 3/8" | m3 | 2026-10-01 | 89 | 130 | 320 | 310.854 | 98.146 | 75.5% | OK | Opening count (sample)
Sights Bay | ADM | Admixture | L | 2026-10-01 | 460 | 700 | 1200 | 1243.416 | 416.584 | 59.51% | OK | Opening count (sample)
Tayabas | CEM | Cement | bags | 2026-10-01 | 510 | 750 | 500 | 767.556 | 242.444 | 32.33% | OK | Opening count (sample)
Tayabas | SAND | Sand | m3 | 2026-10-31 | 0 | 48 | 0 | 0 | 0 | 0% | OK | Recount 31-Oct: stockpile empty (remnant unusable)
Tayabas | G38 | Gravel 3/8" | m3 | 2026-10-01 | 26 | 48 | 80 | 63.963 | 42.037 | 87.58% | OK | Opening count (sample)
Tayabas | ADM | Admixture | L | 2026-10-01 | 460 | 600 | 0 | 255.852 | 204.148 | 34.02% | OK | Opening count (sample)
Batulao Impression | CEM | Cement | bags | 2026-10-01 | 820 | 1400 | 2500 | 3092.271 | 227.729 | 16.27% | OK | Opening count (sample)
Batulao Impression | SAND | Sand | m3 | 2026-10-01 | 38 | 70 | 128 | 138.3865 | 27.6135 | 39.45% | OK | Opening count (sample)
Batulao Impression | G34 | Gravel 3/4" | m3 | 2026-10-01 | 22 | 48 | 96 | 76.335 | 41.665 | 86.8% | OK | Opening count (sample)
Batulao Impression | G38 | Gravel 3/8" | m3 | 2026-10-01 | 70 | 90 | 176 | 200.438 | 45.562 | 50.62% | OK | Opening count (sample)
Batulao Impression | ADM | Admixture | L | 2026-10-01 | 400 | 600 | 800 | 992.5895 | 207.4105 | 34.57% | OK | Opening count (sample)

## Consumption Log
2 · Consumption Log — Concrete Produced (m3) by Mix Design
Declare the m3 of concrete produced per day (or per pour/shift). Material used = m3 × mix design quantity × (1 + allowance), and is deducted from stock automatically.
Date | Site / Project | Mix Code | Concrete Produced (m3) | Mix Description | Cement used (bags) | Sand used (m3) | Gravel 3/4" used (m3) | Gravel 3/8" used (m3) | Admixture used (L) | Element / Remarks | Check
2026-10-01 | Example Site | MD-01 | 18.5 | Precast Wall Panel | (auto) | (auto) | (auto) | (auto) | (auto) | Example row — wall panels, casting beds 1-3
2026-10-01 | Batulao Parkhomes | MD-01 | 16.3 | Precast Wall Panel | 201.468 | 8.3945 | 0 | 16.789 | 67.156 | Wall panels | OK
2026-10-01 | Batulao Parkhomes | MD-02 | 3.1 | Precast Slab / Beam | 38.316 | 1.5965 | 3.193 | 0 | 12.772 | Slabs / beams | OK
2026-10-01 | Calauan (Alora+Amani) | MD-01 | 22.2 | Precast Wall Panel | 274.392 | 11.433 | 0 | 22.866 | 91.464 | Wall panels | OK
2026-10-01 | Calauan (Alora+Amani) | MD-03 | 4 | Footing / Ground Slab | 37.8 | 2.1 | 4.2 | 0 | 10.5 | Footings | OK
2026-10-01 | Naic | MD-01 | 26 | Precast Wall Panel | 321.36 | 13.39 | 0 | 26.78 | 107.12 | Wall panels | OK
2026-10-01 | Naic | MD-02 | 5.2 | Precast Slab / Beam | 64.272 | 2.678 | 5.356 | 0 | 21.424 | Slabs / beams | OK
2026-10-01 | The Cove Lipa | MD-01 | 18.8 | Precast Wall Panel | 232.368 | 9.682 | 0 | 19.364 | 77.456 | Wall panels | OK
2026-10-01 | The Cove Lipa | MD-04 | 1.7 | Lean Concrete / Blinding | 10.71 | 0.8925 | 1.785 | 0 | 0 | Lean concrete | OK
2026-10-01 | Sights Bay | MD-01 | 12.4 | Precast Wall Panel | 153.264 | 6.386 | 0 | 12.772 | 51.088 | Wall panels | OK
2026-10-01 | Tayabas | MD-01 | 3.3 | Precast Wall Panel | 40.788 | 1.6995 | 0 | 3.399 | 13.596 | Wall panels | OK
2026-10-01 | Batulao Impression | MD-01 | 8.3 | Precast Wall Panel | 102.588 | 4.2745 | 0 | 8.549 | 34.196 | Wall panels | OK
2026-10-01 | Batulao Impression | MD-03 | 3.1 | Footing / Ground Slab | 29.295 | 1.6275 | 3.255 | 0 | 8.1375 | Footings | OK
2026-10-02 | Calauan (Alora+Amani) | MD-01 | 18.3 | Precast Wall Panel | 226.188 | 9.4245 | 0 | 18.849 | 75.396 | Wall panels | OK
2026-10-02 | Calauan (Alora+Amani) | MD-03 | 3.3 | Footing / Ground Slab | 31.185 | 1.7325 | 3.465 | 0 | 8.6625 | Footings | OK
2026-10-02 | Gentri | MD-01 | 8.8 | Precast Wall Panel | 108.768 | 4.532 | 0 | 9.064 | 36.256 | Wall panels | OK
2026-10-02 | Naic | MD-01 | 29.5 | Precast Wall Panel | 364.62 | 15.1925 | 0 | 30.385 | 121.54 | Wall panels | OK
2026-10-02 | Naic | MD-02 | 5.9 | Precast Slab / Beam | 72.924 | 3.0385 | 6.077 | 0 | 24.308 | Slabs / beams | OK
2026-10-02 | The Cove Lipa | MD-01 | 19.6 | Precast Wall Panel | 242.256 | 10.094 | 0 | 20.188 | 80.752 | Wall panels | OK
2026-10-02 | The Cove Lipa | MD-04 | 1.8 | Lean Concrete / Blinding | 11.34 | 0.945 | 1.89 | 0 | 0 | Lean concrete | OK
2026-10-02 | Sights Bay | MD-01 | 13 | Precast Wall Panel | 160.68 | 6.695 | 0 | 13.39 | 53.56 | Wall panels | OK
2026-10-02 | Tayabas | MD-01 | 3.1 | Precast Wall Panel | 38.316 | 1.5965 | 0 | 3.193 | 12.772 | Wall panels | OK
2026-10-02 | Batulao Impression | MD-01 | 8.3 | Precast Wall Panel | 102.588 | 4.2745 | 0 | 8.549 | 34.196 | Wall panels | OK
2026-10-02 | Batulao Impression | MD-03 | 3.1 | Footing / Ground Slab | 29.295 | 1.6275 | 3.255 | 0 | 8.1375 | Footings | OK
2026-10-03 | Batulao Parkhomes | MD-01 | 14.5 | Precast Wall Panel | 179.22 | 7.4675 | 0 | 14.935 | 59.74 | Wall panels | OK
2026-10-03 | Batulao Parkhomes | MD-02 | 2.7 | Precast Slab / Beam | 33.372 | 1.3905 | 2.781 | 0 | 11.124 | Slabs / beams | OK
2026-10-03 | Calauan (Alora+Amani) | MD-01 | 20.3 | Precast Wall Panel | 250.908 | 10.4545 | 0 | 20.909 | 83.636 | Wall panels | OK
2026-10-03 | Calauan (Alora+Amani) | MD-03 | 3.7 | Footing / Ground Slab | 34.965 | 1.9425 | 3.885 | 0 | 9.7125 | Footings | OK
2026-10-03 | Gentri | MD-01 | 9.2 | Precast Wall Panel | 113.712 | 4.738 | 0 | 9.476 | 37.904 | Wall panels | OK
2026-10-03 | Naic | MD-01 | 27.2 | Precast Wall Panel | 336.192 | 14.008 | 0 | 28.016 | 112.064 | Wall panels | OK
2026-10-03 | Naic | MD-02 | 5.4 | Precast Slab / Beam | 66.744 | 2.781 | 5.562 | 0 | 22.248 | Slabs / beams | OK
2026-10-03 | The Cove Lipa | MD-01 | 19.4 | Precast Wall Panel | 239.784 | 9.991 | 0 | 19.982 | 79.928 | Wall panels | OK
2026-10-03 | The Cove Lipa | MD-04 | 1.8 | Lean Concrete / Blinding | 11.34 | 0.945 | 1.89 | 0 | 0 | Lean concrete | OK
2026-10-03 | Sights Bay | MD-01 | 13.2 | Precast Wall Panel | 163.152 | 6.798 | 0 | 13.596 | 54.384 | Wall panels | OK
2026-10-03 | Tayabas | MD-01 | 2.7 | Precast Wall Panel | 33.372 | 1.3905 | 0 | 2.781 | 11.124 | Wall panels | OK
2026-10-05 | Batulao Parkhomes | MD-01 | 17 | Precast Wall Panel | 210.12 | 8.755 | 0 | 17.51 | 70.04 | Wall panels | OK
2026-10-05 | Batulao Parkhomes | MD-02 | 3.2 | Precast Slab / Beam | 39.552 | 1.648 | 3.296 | 0 | 13.184 | Slabs / beams | OK
2026-10-05 | Calauan (Alora+Amani) | MD-01 | 18.8 | Precast Wall Panel | 232.368 | 9.682 | 0 | 19.364 | 77.456 | Wall panels | OK
2026-10-05 | Calauan (Alora+Amani) | MD-03 | 3.4 | Footing / Ground Slab | 32.13 | 1.785 | 3.57 | 0 | 8.925 | Footings | OK
2026-10-05 | Gentri | MD-01 | 10 | Precast Wall Panel | 123.6 | 5.15 | 0 | 10.3 | 41.2 | Wall panels | OK
2026-10-05 | Naic | MD-01 | 26.1 | Precast Wall Panel | 322.596 | 13.4415 | 0 | 26.883 | 107.532 | Wall panels | OK
2026-10-05 | Naic | MD-02 | 5.2 | Precast Slab / Beam | 64.272 | 2.678 | 5.356 | 0 | 21.424 | Slabs / beams | OK
2026-10-05 | The Cove Lipa | MD-01 | 24.3 | Precast Wall Panel | 300.348 | 12.5145 | 0 | 25.029 | 100.116 | Wall panels | OK
2026-10-05 | The Cove Lipa | MD-04 | 2.2 | Lean Concrete / Blinding | 13.86 | 1.155 | 2.31 | 0 | 0 | Lean concrete | OK
2026-10-05 | Sights Bay | MD-01 | 10.4 | Precast Wall Panel | 128.544 | 5.356 | 0 | 10.712 | 42.848 | Wall panels | OK
2026-10-05 | Tayabas | MD-01 | 2.7 | Precast Wall Panel | 33.372 | 1.3905 | 0 | 2.781 | 11.124 | Wall panels | OK
2026-10-05 | Batulao Impression | MD-01 | 6.7 | Precast Wall Panel | 82.812 | 3.4505 | 0 | 6.901 | 27.604 | Wall panels | OK
2026-10-05 | Batulao Impression | MD-03 | 2.5 | Footing / Ground Slab | 23.625 | 1.3125 | 2.625 | 0 | 6.5625 | Footings | OK
2026-10-06 | Batulao Parkhomes | MD-01 | 17.3 | Precast Wall Panel | 213.828 | 8.9095 | 0 | 17.819 | 71.276 | Wall panels | OK
2026-10-06 | Batulao Parkhomes | MD-02 | 3.3 | Precast Slab / Beam | 40.788 | 1.6995 | 3.399 | 0 | 13.596 | Slabs / beams | OK
2026-10-06 | Calauan (Alora+Amani) | MD-01 | 19.8 | Precast Wall Panel | 244.728 | 10.197 | 0 | 20.394 | 81.576 | Wall panels | OK
2026-10-06 | Calauan (Alora+Amani) | MD-03 | 3.6 | Footing / Ground Slab | 34.02 | 1.89 | 3.78 | 0 | 9.45 | Footings | OK
2026-10-06 | Gentri | MD-01 | 9.5 | Precast Wall Panel | 117.42 | 4.8925 | 0 | 9.785 | 39.14 | Wall panels | OK
2026-10-06 | Naic | MD-01 | 33.1 | Precast Wall Panel | 409.116 | 17.0465 | 0 | 34.093 | 136.372 | Wall panels | OK
2026-10-06 | Naic | MD-02 | 6.6 | Precast Slab / Beam | 81.576 | 3.399 | 6.798 | 0 | 27.192 | Slabs / beams | OK
2026-10-06 | The Cove Lipa | MD-01 | 19.9 | Precast Wall Panel | 245.964 | 10.2485 | 0 | 20.497 | 81.988 | Wall panels | OK
2026-10-06 | The Cove Lipa | MD-04 | 1.8 | Lean Concrete / Blinding | 11.34 | 0.945 | 1.89 | 0 | 0 | Lean concrete | OK
2026-10-06 | Sights Bay | MD-01 | 12.7 | Precast Wall Panel | 156.972 | 6.5405 | 0 | 13.081 | 52.324 | Wall panels | OK
2026-10-06 | Tayabas | MD-01 | 2.9 | Precast Wall Panel | 35.844 | 1.4935 | 0 | 2.987 | 11.948 | Wall panels | OK
2026-10-07 | Batulao Parkhomes | MD-01 | 15.8 | Precast Wall Panel | 195.288 | 8.137 | 0 | 16.274 | 65.096 | Wall panels | OK
2026-10-07 | Batulao Parkhomes | MD-02 | 3 | Precast Slab / Beam | 37.08 | 1.545 | 3.09 | 0 | 12.36 | Slabs / beams | OK
2026-10-07 | Calauan (Alora+Amani) | MD-01 | 23.1 | Precast Wall Panel | 285.516 | 11.8965 | 0 | 23.793 | 95.172 | Wall panels | OK
2026-10-07 | Calauan (Alora+Amani) | MD-03 | 4.2 | Footing / Ground Slab | 39.69 | 2.205 | 4.41 | 0 | 11.025 | Footings | OK
2026-10-07 | Gentri | MD-01 | 9.3 | Precast Wall Panel | 114.948 | 4.7895 | 0 | 9.579 | 38.316 | Wall panels | OK
2026-10-07 | Naic | MD-01 | 26.1 | Precast Wall Panel | 322.596 | 13.4415 | 0 | 26.883 | 107.532 | Wall panels | OK
2026-10-07 | Naic | MD-02 | 5.2 | Precast Slab / Beam | 64.272 | 2.678 | 5.356 | 0 | 21.424 | Slabs / beams | OK
2026-10-07 | The Cove Lipa | MD-01 | 23.2 | Precast Wall Panel | 286.752 | 11.948 | 0 | 23.896 | 95.584 | Wall panels | OK
2026-10-07 | The Cove Lipa | MD-04 | 2.1 | Lean Concrete / Blinding | 13.23 | 1.1025 | 2.205 | 0 | 0 | Lean concrete | OK
2026-10-07 | Sights Bay | MD-01 | 13.4 | Precast Wall Panel | 165.624 | 6.901 | 0 | 13.802 | 55.208 | Wall panels | OK
2026-10-07 | Tayabas | MD-01 | 3.3 | Precast Wall Panel | 40.788 | 1.6995 | 0 | 3.399 | 13.596 | Wall panels | OK
2026-10-07 | Batulao Impression | MD-01 | 8.6 | Precast Wall Panel | 106.296 | 4.429 | 0 | 8.858 | 35.432 | Wall panels | OK
2026-10-07 | Batulao Impression | MD-03 | 3.2 | Footing / Ground Slab | 30.24 | 1.68 | 3.36 | 0 | 8.4 | Footings | OK
2026-10-08 | Batulao Parkhomes | MD-01 | 14.8 | Precast Wall Panel | 182.928 | 7.622 | 0 | 15.244 | 60.976 | Wall panels | OK
2026-10-08 | Batulao Parkhomes | MD-02 | 2.8 | Precast Slab / Beam | 34.608 | 1.442 | 2.884 | 0 | 11.536 | Slabs / beams | OK
2026-10-08 | Calauan (Alora+Amani) | MD-01 | 21.8 | Precast Wall Panel | 269.448 | 11.227 | 0 | 22.454 | 89.816 | Wall panels | OK
2026-10-08 | Calauan (Alora+Amani) | MD-03 | 4 | Footing / Ground Slab | 37.8 | 2.1 | 4.2 | 0 | 10.5 | Footings | OK
2026-10-08 | Gentri | MD-01 | 10.1 | Precast Wall Panel | 124.836 | 5.2015 | 0 | 10.403 | 41.612 | Wall panels | OK
2026-10-08 | Naic | MD-01 | 28.1 | Precast Wall Panel | 347.316 | 14.4715 | 0 | 28.943 | 115.772 | Wall panels | OK
2026-10-08 | Naic | MD-02 | 5.6 | Precast Slab / Beam | 69.216 | 2.884 | 5.768 | 0 | 23.072 | Slabs / beams | OK
2026-10-08 | The Cove Lipa | MD-01 | 22.7 | Precast Wall Panel | 280.572 | 11.6905 | 0 | 23.381 | 93.524 | Wall panels | OK
2026-10-08 | The Cove Lipa | MD-04 | 2.1 | Lean Concrete / Blinding | 13.23 | 1.1025 | 2.205 | 0 | 0 | Lean concrete | OK
2026-10-08 | Sights Bay | MD-01 | 9.9 | Precast Wall Panel | 122.364 | 5.0985 | 0 | 10.197 | 40.788 | Wall panels | OK
2026-10-08 | Tayabas | MD-01 | 2.9 | Precast Wall Panel | 35.844 | 1.4935 | 0 | 2.987 | 11.948 | Wall panels | OK
2026-10-08 | Batulao Impression | MD-01 | 7.3 | Precast Wall Panel | 90.228 | 3.7595 | 0 | 7.519 | 30.076 | Wall panels | OK
2026-10-08 | Batulao Impression | MD-03 | 2.7 | Footing / Ground Slab | 25.515 | 1.4175 | 2.835 | 0 | 7.0875 | Footings | OK
2026-10-09 | Batulao Parkhomes | MD-01 | 17 | Precast Wall Panel | 210.12 | 8.755 | 0 | 17.51 | 70.04 | Wall panels | OK
2026-10-09 | Batulao Parkhomes | MD-02 | 3.2 | Precast Slab / Beam | 39.552 | 1.648 | 3.296 | 0 | 13.184 | Slabs / beams | OK
2026-10-09 | Calauan (Alora+Amani) | MD-01 | 18.6 | Precast Wall Panel | 229.896 | 9.579 | 0 | 19.158 | 76.632 | Wall panels | OK
2026-10-09 | Calauan (Alora+Amani) | MD-03 | 3.4 | Footing / Ground Slab | 32.13 | 1.785 | 3.57 | 0 | 8.925 | Footings | OK
2026-10-09 | Gentri | MD-01 | 10.5 | Precast Wall Panel | 129.78 | 5.4075 | 0 | 10.815 | 43.26 | Wall panels | OK
2026-10-09 | Naic | MD-01 | 32.1 | Precast Wall Panel | 396.756 | 16.5315 | 0 | 33.063 | 132.252 | Wall panels | OK
2026-10-09 | Naic | MD-02 | 6.4 | Precast Slab / Beam | 79.104 | 3.296 | 6.592 | 0 | 26.368 | Slabs / beams | OK
2026-10-09 | The Cove Lipa | MD-01 | 21.3 | Precast Wall Panel | 263.268 | 10.9695 | 0 | 21.939 | 87.756 | Wall panels | OK
2026-10-09 | The Cove Lipa | MD-04 | 1.9 | Lean Concrete / Blinding | 11.97 | 0.9975 | 1.995 | 0 | 0 | Lean concrete | OK
2026-10-09 | Sights Bay | MD-01 | 11.9 | Precast Wall Panel | 147.084 | 6.1285 | 0 | 12.257 | 49.028 | Wall panels | OK
2026-10-09 | Tayabas | MD-01 | 3.1 | Precast Wall Panel | 38.316 | 1.5965 | 0 | 3.193 | 12.772 | Wall panels | OK
2026-10-09 | Batulao Impression | MD-01 | 8.1 | Precast Wall Panel | 100.116 | 4.1715 | 0 | 8.343 | 33.372 | Wall panels | OK
2026-10-09 | Batulao Impression | MD-03 | 3 | Footing / Ground Slab | 28.35 | 1.575 | 3.15 | 0 | 7.875 | Footings | OK
2026-10-10 | Batulao Parkhomes | MD-01 | 15.7 | Precast Wall Panel | 194.052 | 8.0855 | 0 | 16.171 | 64.684 | Wall panels | OK
2026-10-10 | Batulao Parkhomes | MD-02 | 2.9 | Precast Slab / Beam | 35.844 | 1.4935 | 2.987 | 0 | 11.948 | Slabs / beams | OK
2026-10-10 | Calauan (Alora+Amani) | MD-01 | 21.3 | Precast Wall Panel | 263.268 | 10.9695 | 0 | 21.939 | 87.756 | Wall panels | OK
2026-10-10 | Calauan (Alora+Amani) | MD-03 | 3.9 | Footing / Ground Slab | 36.855 | 2.0475 | 4.095 | 0 | 10.2375 | Footings | OK
2026-10-10 | Gentri | MD-01 | 8.9 | Precast Wall Panel | 110.004 | 4.5835 | 0 | 9.167 | 36.668 | Wall panels | OK
2026-10-10 | Naic | MD-01 | 26.2 | Precast Wall Panel | 323.832 | 13.493 | 0 | 26.986 | 107.944 | Wall panels | OK
2026-10-10 | Naic | MD-02 | 5.2 | Precast Slab / Beam | 64.272 | 2.678 | 5.356 | 0 | 21.424 | Slabs / beams | OK
2026-10-10 | The Cove Lipa | MD-01 | 18.9 | Precast Wall Panel | 233.604 | 9.7335 | 0 | 19.467 | 77.868 | Wall panels | OK
2026-10-10 | The Cove Lipa | MD-04 | 1.7 | Lean Concrete / Blinding | 10.71 | 0.8925 | 1.785 | 0 | 0 | Lean concrete | OK
2026-10-10 | Sights Bay | MD-01 | 11.4 | Precast Wall Panel | 140.904 | 5.871 | 0 | 11.742 | 46.968 | Wall panels | OK
2026-10-10 | Tayabas | MD-01 | 2.9 | Precast Wall Panel | 35.844 | 1.4935 | 0 | 2.987 | 11.948 | Wall panels | OK
2026-10-10 | Batulao Impression | MD-01 | 8.3 | Precast Wall Panel | 102.588 | 4.2745 | 0 | 8.549 | 34.196 | Wall panels | OK
2026-10-10 | Batulao Impression | MD-03 | 3.1 | Footing / Ground Slab | 29.295 | 1.6275 | 3.255 | 0 | 8.1375 | Footings | OK
2026-10-12 | Batulao Parkhomes | MD-01 | 16.3 | Precast Wall Panel | 201.468 | 8.3945 | 0 | 16.789 | 67.156 | Wall panels | OK
2026-10-12 | Batulao Parkhomes | MD-02 | 3.1 | Precast Slab / Beam | 38.316 | 1.5965 | 3.193 | 0 | 12.772 | Slabs / beams | OK
2026-10-12 | Calauan (Alora+Amani) | MD-01 | 19 | Precast Wall Panel | 234.84 | 9.785 | 0 | 19.57 | 78.28 | Wall panels | OK
2026-10-12 | Calauan (Alora+Amani) | MD-03 | 3.5 | Footing / Ground Slab | 33.075 | 1.8375 | 3.675 | 0 | 9.1875 | Footings | OK
2026-10-12 | Gentri | MD-01 | 10.6 | Precast Wall Panel | 131.016 | 5.459 | 0 | 10.918 | 43.672 | Wall panels | OK
2026-10-12 | Naic | MD-01 | 28.8 | Precast Wall Panel | 355.968 | 14.832 | 0 | 29.664 | 118.656 | Wall panels | OK
2026-10-12 | Naic | MD-02 | 5.8 | Precast Slab / Beam | 71.688 | 2.987 | 5.974 | 0 | 23.896 | Slabs / beams | OK
2026-10-12 | The Cove Lipa | MD-01 | 20.1 | Precast Wall Panel | 248.436 | 10.3515 | 0 | 20.703 | 82.812 | Wall panels | OK
2026-10-12 | The Cove Lipa | MD-04 | 1.8 | Lean Concrete / Blinding | 11.34 | 0.945 | 1.89 | 0 | 0 | Lean concrete | OK
2026-10-12 | Sights Bay | MD-01 | 11.7 | Precast Wall Panel | 144.612 | 6.0255 | 0 | 12.051 | 48.204 | Wall panels | OK
2026-10-12 | Tayabas | MD-01 | 3.2 | Precast Wall Panel | 39.552 | 1.648 | 0 | 3.296 | 13.184 | Wall panels | OK
2026-10-12 | Batulao Impression | MD-01 | 8.8 | Precast Wall Panel | 108.768 | 4.532 | 0 | 9.064 | 36.256 | Wall panels | OK
2026-10-12 | Batulao Impression | MD-03 | 3.3 | Footing / Ground Slab | 31.185 | 1.7325 | 3.465 | 0 | 8.6625 | Footings | OK
2026-10-13 | Batulao Parkhomes | MD-01 | 15.7 | Precast Wall Panel | 194.052 | 8.0855 | 0 | 16.171 | 64.684 | Wall panels | OK
2026-10-13 | Batulao Parkhomes | MD-02 | 2.9 | Precast Slab / Beam | 35.844 | 1.4935 | 2.987 | 0 | 11.948 | Slabs / beams | OK
2026-10-13 | Calauan (Alora+Amani) | MD-01 | 20.8 | Precast Wall Panel | 257.088 | 10.712 | 0 | 21.424 | 85.696 | Wall panels | OK
2026-10-13 | Calauan (Alora+Amani) | MD-03 | 3.8 | Footing / Ground Slab | 35.91 | 1.995 | 3.99 | 0 | 9.975 | Footings | OK
2026-10-13 | Gentri | MD-01 | 10.2 | Precast Wall Panel | 126.072 | 5.253 | 0 | 10.506 | 42.024 | Wall panels | OK
2026-10-13 | Naic | MD-01 | 32.2 | Precast Wall Panel | 397.992 | 16.583 | 0 | 33.166 | 132.664 | Wall panels | OK
2026-10-13 | Naic | MD-02 | 6.4 | Precast Slab / Beam | 79.104 | 3.296 | 6.592 | 0 | 26.368 | Slabs / beams | OK
2026-10-13 | The Cove Lipa | MD-01 | 24.2 | Precast Wall Panel | 299.112 | 12.463 | 0 | 24.926 | 99.704 | Wall panels | OK
2026-10-13 | The Cove Lipa | MD-04 | 2.2 | Lean Concrete / Blinding | 13.86 | 1.155 | 2.31 | 0 | 0 | Lean concrete | OK
2026-10-13 | Sights Bay | MD-01 | 12.6 | Precast Wall Panel | 155.736 | 6.489 | 0 | 12.978 | 51.912 | Wall panels | OK
2026-10-13 | Tayabas | MD-01 | 3.3 | Precast Wall Panel | 40.788 | 1.6995 | 0 | 3.399 | 13.596 | Wall panels | OK
2026-10-13 | Batulao Impression | MD-01 | 8.8 | Precast Wall Panel | 108.768 | 4.532 | 0 | 9.064 | 36.256 | Wall panels | OK
2026-10-13 | Batulao Impression | MD-03 | 3.3 | Footing / Ground Slab | 31.185 | 1.7325 | 3.465 | 0 | 8.6625 | Footings | OK
2026-10-14 | Batulao Parkhomes | MD-01 | 17 | Precast Wall Panel | 210.12 | 8.755 | 0 | 17.51 | 70.04 | Wall panels | OK
2026-10-14 | Batulao Parkhomes | MD-02 | 3.2 | Precast Slab / Beam | 39.552 | 1.648 | 3.296 | 0 | 13.184 | Slabs / beams | OK
2026-10-14 | Calauan (Alora+Amani) | MD-01 | 21.1 | Precast Wall Panel | 260.796 | 10.8665 | 0 | 21.733 | 86.932 | Wall panels | OK
2026-10-14 | Calauan (Alora+Amani) | MD-03 | 3.8 | Footing / Ground Slab | 35.91 | 1.995 | 3.99 | 0 | 9.975 | Footings | OK
2026-10-14 | Gentri | MD-01 | 10 | Precast Wall Panel | 123.6 | 5.15 | 0 | 10.3 | 41.2 | Wall panels | OK
2026-10-14 | Naic | MD-01 | 27.9 | Precast Wall Panel | 344.844 | 14.3685 | 0 | 28.737 | 114.948 | Wall panels | OK
2026-10-14 | Naic | MD-02 | 5.6 | Precast Slab / Beam | 69.216 | 2.884 | 5.768 | 0 | 23.072 | Slabs / beams | OK
2026-10-14 | The Cove Lipa | MD-01 | 22 | Precast Wall Panel | 271.92 | 11.33 | 0 | 22.66 | 90.64 | Wall panels | OK
2026-10-14 | The Cove Lipa | MD-04 | 2 | Lean Concrete / Blinding | 12.6 | 1.05 | 2.1 | 0 | 0 | Lean concrete | OK
2026-10-14 | Sights Bay | MD-01 | 9.9 | Precast Wall Panel | 122.364 | 5.0985 | 0 | 10.197 | 40.788 | Wall panels | OK
2026-10-14 | Tayabas | MD-01 | 2.8 | Precast Wall Panel | 34.608 | 1.442 | 0 | 2.884 | 11.536 | Wall panels | OK
2026-10-14 | Batulao Impression | MD-01 | 8.7 | Precast Wall Panel | 107.532 | 4.4805 | 0 | 8.961 | 35.844 | Wall panels | OK
2026-10-14 | Batulao Impression | MD-03 | 3.3 | Footing / Ground Slab | 31.185 | 1.7325 | 3.465 | 0 | 8.6625 | Footings | OK
2026-10-15 | Batulao Parkhomes | MD-01 | 13.3 | Precast Wall Panel | 164.388 | 6.8495 | 0 | 13.699 | 54.796 | Wall panels | OK
2026-10-15 | Batulao Parkhomes | MD-02 | 2.5 | Precast Slab / Beam | 30.9 | 1.2875 | 2.575 | 0 | 10.3 | Slabs / beams | OK
2026-10-15 | Calauan (Alora+Amani) | MD-01 | 23.3 | Precast Wall Panel | 287.988 | 11.9995 | 0 | 23.999 | 95.996 | Wall panels | OK
2026-10-15 | Calauan (Alora+Amani) | MD-03 | 4.2 | Footing / Ground Slab | 39.69 | 2.205 | 4.41 | 0 | 11.025 | Footings | OK
2026-10-15 | Gentri | MD-01 | 10.5 | Precast Wall Panel | 129.78 | 5.4075 | 0 | 10.815 | 43.26 | Wall panels | OK
2026-10-15 | The Cove Lipa | MD-01 | 21.8 | Precast Wall Panel | 269.448 | 11.227 | 0 | 22.454 | 89.816 | Wall panels | OK
2026-10-15 | The Cove Lipa | MD-04 | 2 | Lean Concrete / Blinding | 12.6 | 1.05 | 2.1 | 0 | 0 | Lean concrete | OK
2026-10-15 | Sights Bay | MD-01 | 11.6 | Precast Wall Panel | 143.376 | 5.974 | 0 | 11.948 | 47.792 | Wall panels | OK
2026-10-15 | Tayabas | MD-01 | 2.9 | Precast Wall Panel | 35.844 | 1.4935 | 0 | 2.987 | 11.948 | Wall panels | OK
2026-10-15 | Batulao Impression | MD-01 | 8.1 | Precast Wall Panel | 100.116 | 4.1715 | 0 | 8.343 | 33.372 | Wall panels | OK
2026-10-15 | Batulao Impression | MD-03 | 3.1 | Footing / Ground Slab | 29.295 | 1.6275 | 3.255 | 0 | 8.1375 | Footings | OK
2026-10-16 | Batulao Parkhomes | MD-01 | 14.8 | Precast Wall Panel | 182.928 | 7.622 | 0 | 15.244 | 60.976 | Wall panels | OK
2026-10-16 | Batulao Parkhomes | MD-02 | 2.8 | Precast Slab / Beam | 34.608 | 1.442 | 2.884 | 0 | 11.536 | Slabs / beams | OK
2026-10-16 | Calauan (Alora+Amani) | MD-01 | 21.4 | Precast Wall Panel | 264.504 | 11.021 | 0 | 22.042 | 88.168 | Wall panels | OK
2026-10-16 | Calauan (Alora+Amani) | MD-03 | 3.9 | Footing / Ground Slab | 36.855 | 2.0475 | 4.095 | 0 | 10.2375 | Footings | OK
2026-10-16 | Gentri | MD-01 | 8.8 | Precast Wall Panel | 108.768 | 4.532 | 0 | 9.064 | 36.256 | Wall panels | OK
2026-10-16 | Naic | MD-01 | 25.8 | Precast Wall Panel | 318.888 | 13.287 | 0 | 26.574 | 106.296 | Wall panels | OK
2026-10-16 | Naic | MD-02 | 5.2 | Precast Slab / Beam | 64.272 | 2.678 | 5.356 | 0 | 21.424 | Slabs / beams | OK
2026-10-16 | The Cove Lipa | MD-01 | 24.3 | Precast Wall Panel | 300.348 | 12.5145 | 0 | 25.029 | 100.116 | Wall panels | OK
2026-10-16 | The Cove Lipa | MD-04 | 2.2 | Lean Concrete / Blinding | 13.86 | 1.155 | 2.31 | 0 | 0 | Lean concrete | OK
2026-10-16 | Sights Bay | MD-01 | 11.9 | Precast Wall Panel | 147.084 | 6.1285 | 0 | 12.257 | 49.028 | Wall panels | OK
2026-10-16 | Tayabas | MD-01 | 3.4 | Precast Wall Panel | 42.024 | 1.751 | 0 | 3.502 | 14.008 | Wall panels | OK
2026-10-16 | Batulao Impression | MD-01 | 6.7 | Precast Wall Panel | 82.812 | 3.4505 | 0 | 6.901 | 27.604 | Wall panels | OK
2026-10-16 | Batulao Impression | MD-03 | 2.5 | Footing / Ground Slab | 23.625 | 1.3125 | 2.625 | 0 | 6.5625 | Footings | OK
2026-10-17 | Batulao Parkhomes | MD-01 | 15.9 | Precast Wall Panel | 196.524 | 8.1885 | 0 | 16.377 | 65.508 | Wall panels | OK
2026-10-17 | Batulao Parkhomes | MD-02 | 3 | Precast Slab / Beam | 37.08 | 1.545 | 3.09 | 0 | 12.36 | Slabs / beams | OK
2026-10-17 | Calauan (Alora+Amani) | MD-01 | 23.8 | Precast Wall Panel | 294.168 | 12.257 | 0 | 24.514 | 98.056 | Wall panels | OK
2026-10-17 | Calauan (Alora+Amani) | MD-03 | 4.3 | Footing / Ground Slab | 40.635 | 2.2575 | 4.515 | 0 | 11.2875 | Footings | OK
2026-10-17 | Gentri | MD-01 | 8.6 | Precast Wall Panel | 106.296 | 4.429 | 0 | 8.858 | 35.432 | Wall panels | OK
2026-10-17 | Naic | MD-01 | 30.8 | Precast Wall Panel | 380.688 | 15.862 | 0 | 31.724 | 126.896 | Wall panels | OK
2026-10-17 | Naic | MD-02 | 6.2 | Precast Slab / Beam | 76.632 | 3.193 | 6.386 | 0 | 25.544 | Slabs / beams | OK
2026-10-17 | Sights Bay | MD-01 | 12.9 | Precast Wall Panel | 159.444 | 6.6435 | 0 | 13.287 | 53.148 | Wall panels | OK
2026-10-17 | Tayabas | MD-01 | 2.8 | Precast Wall Panel | 34.608 | 1.442 | 0 | 2.884 | 11.536 | Wall panels | OK
2026-10-17 | Batulao Impression | MD-01 | 8.1 | Precast Wall Panel | 100.116 | 4.1715 | 0 | 8.343 | 33.372 | Wall panels | OK
2026-10-17 | Batulao Impression | MD-03 | 3 | Footing / Ground Slab | 28.35 | 1.575 | 3.15 | 0 | 7.875 | Footings | OK
2026-10-19 | Batulao Parkhomes | MD-01 | 17.7 | Precast Wall Panel | 218.772 | 9.1155 | 0 | 18.231 | 72.924 | Wall panels | OK
2026-10-19 | Batulao Parkhomes | MD-02 | 3.3 | Precast Slab / Beam | 40.788 | 1.6995 | 3.399 | 0 | 13.596 | Slabs / beams | OK
2026-10-19 | Calauan (Alora+Amani) | MD-01 | 21.2 | Precast Wall Panel | 262.032 | 10.918 | 0 | 21.836 | 87.344 | Wall panels | OK
2026-10-19 | Calauan (Alora+Amani) | MD-03 | 3.9 | Footing / Ground Slab | 36.855 | 2.0475 | 4.095 | 0 | 10.2375 | Footings | OK
2026-10-19 | Gentri | MD-01 | 10.5 | Precast Wall Panel | 129.78 | 5.4075 | 0 | 10.815 | 43.26 | Wall panels | OK
2026-10-19 | Naic | MD-01 | 25.6 | Precast Wall Panel | 316.416 | 13.184 | 0 | 26.368 | 105.472 | Wall panels | OK
2026-10-19 | Naic | MD-02 | 5.1 | Precast Slab / Beam | 63.036 | 2.6265 | 5.253 | 0 | 21.012 | Slabs / beams | OK
2026-10-19 | The Cove Lipa | MD-01 | 21.2 | Precast Wall Panel | 262.032 | 10.918 | 0 | 21.836 | 87.344 | Wall panels | OK
2026-10-19 | The Cove Lipa | MD-04 | 1.9 | Lean Concrete / Blinding | 11.97 | 0.9975 | 1.995 | 0 | 0 | Lean concrete | OK
2026-10-19 | Sights Bay | MD-01 | 13.1 | Precast Wall Panel | 161.916 | 6.7465 | 0 | 13.493 | 53.972 | Wall panels | OK
2026-10-19 | Tayabas | MD-01 | 2.7 | Precast Wall Panel | 33.372 | 1.3905 | 0 | 2.781 | 11.124 | Wall panels | OK
2026-10-19 | Batulao Impression | MD-01 | 7.1 | Precast Wall Panel | 87.756 | 3.6565 | 0 | 7.313 | 29.252 | Wall panels | OK
2026-10-19 | Batulao Impression | MD-03 | 2.6 | Footing / Ground Slab | 24.57 | 1.365 | 2.73 | 0 | 6.825 | Footings | OK
2026-10-20 | Batulao Parkhomes | MD-01 | 13.1 | Precast Wall Panel | 161.916 | 6.7465 | 0 | 13.493 | 53.972 | Wall panels | OK
2026-10-20 | Batulao Parkhomes | MD-02 | 2.5 | Precast Slab / Beam | 30.9 | 1.2875 | 2.575 | 0 | 10.3 | Slabs / beams | OK
2026-10-20 | Calauan (Alora+Amani) | MD-01 | 23.4 | Precast Wall Panel | 289.224 | 12.051 | 0 | 24.102 | 96.408 | Wall panels | OK
2026-10-20 | Calauan (Alora+Amani) | MD-03 | 4.3 | Footing / Ground Slab | 40.635 | 2.2575 | 4.515 | 0 | 11.2875 | Footings | OK
2026-10-20 | Gentri | MD-01 | 9.7 | Precast Wall Panel | 119.892 | 4.9955 | 0 | 9.991 | 39.964 | Wall panels | OK
2026-10-20 | Naic | MD-01 | 32.8 | Precast Wall Panel | 405.408 | 16.892 | 0 | 33.784 | 135.136 | Wall panels | OK
2026-10-20 | Naic | MD-02 | 6.6 | Precast Slab / Beam | 81.576 | 3.399 | 6.798 | 0 | 27.192 | Slabs / beams | OK
2026-10-20 | The Cove Lipa | MD-01 | 20.7 | Precast Wall Panel | 255.852 | 10.6605 | 0 | 21.321 | 85.284 | Wall panels | OK
2026-10-20 | The Cove Lipa | MD-04 | 1.9 | Lean Concrete / Blinding | 11.97 | 0.9975 | 1.995 | 0 | 0 | Lean concrete | OK
2026-10-20 | Sights Bay | MD-01 | 13.2 | Precast Wall Panel | 163.152 | 6.798 | 0 | 13.596 | 54.384 | Wall panels | OK
2026-10-20 | Tayabas | MD-01 | 2.7 | Precast Wall Panel | 33.372 | 1.3905 | 0 | 2.781 | 11.124 | Wall panels | OK
2026-10-20 | Batulao Impression | MD-01 | 8 | Precast Wall Panel | 98.88 | 4.12 | 0 | 8.24 | 32.96 | Wall panels | OK
2026-10-20 | Batulao Impression | MD-03 | 3 | Footing / Ground Slab | 28.35 | 1.575 | 3.15 | 0 | 7.875 | Footings | OK
2026-10-21 | Batulao Parkhomes | MD-01 | 16 | Precast Wall Panel | 197.76 | 8.24 | 0 | 16.48 | 65.92 | Wall panels | OK
2026-10-21 | Batulao Parkhomes | MD-02 | 3 | Precast Slab / Beam | 37.08 | 1.545 | 3.09 | 0 | 12.36 | Slabs / beams | OK
2026-10-21 | Gentri | MD-01 | 10 | Precast Wall Panel | 123.6 | 5.15 | 0 | 10.3 | 41.2 | Wall panels | OK
2026-10-21 | Naic | MD-01 | 32.9 | Precast Wall Panel | 406.644 | 16.9435 | 0 | 33.887 | 135.548 | Wall panels | OK
2026-10-21 | Naic | MD-02 | 6.6 | Precast Slab / Beam | 81.576 | 3.399 | 6.798 | 0 | 27.192 | Slabs / beams | OK
2026-10-21 | The Cove Lipa | MD-01 | 20.9 | Precast Wall Panel | 258.324 | 10.7635 | 0 | 21.527 | 86.108 | Wall panels | OK
2026-10-21 | The Cove Lipa | MD-04 | 1.9 | Lean Concrete / Blinding | 11.97 | 0.9975 | 1.995 | 0 | 0 | Lean concrete | OK
2026-10-21 | Sights Bay | MD-01 | 11.9 | Precast Wall Panel | 147.084 | 6.1285 | 0 | 12.257 | 49.028 | Wall panels | OK
2026-10-21 | Tayabas | MD-01 | 2.9 | Precast Wall Panel | 35.844 | 1.4935 | 0 | 2.987 | 11.948 | Wall panels | OK
2026-10-21 | Batulao Impression | MD-01 | 7.4 | Precast Wall Panel | 91.464 | 3.811 | 0 | 7.622 | 30.488 | Wall panels | OK
2026-10-21 | Batulao Impression | MD-03 | 2.8 | Footing / Ground Slab | 26.46 | 1.47 | 2.94 | 0 | 7.35 | Footings | OK
2026-10-22 | Batulao Parkhomes | MD-01 | 17.8 | Precast Wall Panel | 220.008 | 9.167 | 0 | 18.334 | 73.336 | Wall panels | OK
2026-10-22 | Batulao Parkhomes | MD-02 | 3.3 | Precast Slab / Beam | 40.788 | 1.6995 | 3.399 | 0 | 13.596 | Slabs / beams | OK
2026-10-22 | Calauan (Alora+Amani) | MD-01 | 24.5 | Precast Wall Panel | 302.82 | 12.6175 | 0 | 25.235 | 100.94 | Wall panels | OK
2026-10-22 | Calauan (Alora+Amani) | MD-03 | 4.5 | Footing / Ground Slab | 42.525 | 2.3625 | 4.725 | 0 | 11.8125 | Footings | OK
2026-10-22 | Gentri | MD-01 | 10.9 | Precast Wall Panel | 134.724 | 5.6135 | 0 | 11.227 | 44.908 | Wall panels | OK
2026-10-22 | Naic | MD-01 | 29.8 | Precast Wall Panel | 368.328 | 15.347 | 0 | 30.694 | 122.776 | Wall panels | OK
2026-10-22 | Naic | MD-02 | 6 | Precast Slab / Beam | 74.16 | 3.09 | 6.18 | 0 | 24.72 | Slabs / beams | OK
2026-10-22 | Sights Bay | MD-01 | 13 | Precast Wall Panel | 160.68 | 6.695 | 0 | 13.39 | 53.56 | Wall panels | OK
2026-10-22 | Tayabas | MD-01 | 2.9 | Precast Wall Panel | 35.844 | 1.4935 | 0 | 2.987 | 11.948 | Wall panels | OK
2026-10-22 | Batulao Impression | MD-01 | 7.8 | Precast Wall Panel | 96.408 | 4.017 | 0 | 8.034 | 32.136 | Wall panels | OK
2026-10-22 | Batulao Impression | MD-03 | 2.9 | Footing / Ground Slab | 27.405 | 1.5225 | 3.045 | 0 | 7.6125 | Footings | OK
2026-10-23 | Batulao Parkhomes | MD-01 | 14.3 | Precast Wall Panel | 176.748 | 7.3645 | 0 | 14.729 | 58.916 | Wall panels | OK
2026-10-23 | Batulao Parkhomes | MD-02 | 2.7 | Precast Slab / Beam | 33.372 | 1.3905 | 2.781 | 0 | 11.124 | Slabs / beams | OK
2026-10-23 | Calauan (Alora+Amani) | MD-01 | 21.9 | Precast Wall Panel | 270.684 | 11.2785 | 0 | 22.557 | 90.228 | Wall panels | OK
2026-10-23 | Calauan (Alora+Amani) | MD-03 | 4 | Footing / Ground Slab | 37.8 | 2.1 | 4.2 | 0 | 10.5 | Footings | OK
2026-10-23 | Gentri | MD-01 | 9.1 | Precast Wall Panel | 112.476 | 4.6865 | 0 | 9.373 | 37.492 | Wall panels | OK
2026-10-23 | Naic | MD-01 | 32.7 | Precast Wall Panel | 404.172 | 16.8405 | 0 | 33.681 | 134.724 | Wall panels | OK
2026-10-23 | Naic | MD-02 | 6.5 | Precast Slab / Beam | 80.34 | 3.3475 | 6.695 | 0 | 26.78 | Slabs / beams | OK
2026-10-23 | The Cove Lipa | MD-01 | 23.3 | Precast Wall Panel | 287.988 | 11.9995 | 0 | 23.999 | 95.996 | Wall panels | OK
2026-10-23 | The Cove Lipa | MD-04 | 2.1 | Lean Concrete / Blinding | 13.23 | 1.1025 | 2.205 | 0 | 0 | Lean concrete | OK
2026-10-23 | Sights Bay | MD-01 | 12.5 | Precast Wall Panel | 154.5 | 6.4375 | 0 | 12.875 | 51.5 | Wall panels | OK
2026-10-23 | Tayabas | MD-01 | 2.8 | Precast Wall Panel | 34.608 | 1.442 | 0 | 2.884 | 11.536 | Wall panels | OK
2026-10-23 | Batulao Impression | MD-01 | 6.9 | Precast Wall Panel | 85.284 | 3.5535 | 0 | 7.107 | 28.428 | Wall panels | OK
2026-10-23 | Batulao Impression | MD-03 | 2.6 | Footing / Ground Slab | 24.57 | 1.365 | 2.73 | 0 | 6.825 | Footings | OK
2026-10-24 | Batulao Parkhomes | MD-01 | 15.1 | Precast Wall Panel | 186.636 | 7.7765 | 0 | 15.553 | 62.212 | Wall panels | OK
2026-10-24 | Batulao Parkhomes | MD-02 | 2.8 | Precast Slab / Beam | 34.608 | 1.442 | 2.884 | 0 | 11.536 | Slabs / beams | OK
2026-10-24 | Calauan (Alora+Amani) | MD-01 | 21.1 | Precast Wall Panel | 260.796 | 10.8665 | 0 | 21.733 | 86.932 | Wall panels | OK
2026-10-24 | Calauan (Alora+Amani) | MD-03 | 3.8 | Footing / Ground Slab | 35.91 | 1.995 | 3.99 | 0 | 9.975 | Footings | OK
2026-10-24 | Naic | MD-01 | 29.4 | Precast Wall Panel | 363.384 | 15.141 | 0 | 30.282 | 121.128 | Wall panels | OK
2026-10-24 | Naic | MD-02 | 5.9 | Precast Slab / Beam | 72.924 | 3.0385 | 6.077 | 0 | 24.308 | Slabs / beams | OK
2026-10-24 | The Cove Lipa | MD-01 | 22.9 | Precast Wall Panel | 283.044 | 11.7935 | 0 | 23.587 | 94.348 | Wall panels | OK
2026-10-24 | The Cove Lipa | MD-04 | 2.1 | Lean Concrete / Blinding | 13.23 | 1.1025 | 2.205 | 0 | 0 | Lean concrete | OK
2026-10-24 | Sights Bay | MD-01 | 12.6 | Precast Wall Panel | 155.736 | 6.489 | 0 | 12.978 | 51.912 | Wall panels | OK
2026-10-24 | Tayabas | MD-01 | 2.8 | Precast Wall Panel | 34.608 | 1.442 | 0 | 2.884 | 11.536 | Wall panels – reduced, material shortage | OK
2026-10-24 | Batulao Impression | MD-01 | 7.8 | Precast Wall Panel | 96.408 | 4.017 | 0 | 8.034 | 32.136 | Wall panels | OK
2026-10-24 | Batulao Impression | MD-03 | 2.9 | Footing / Ground Slab | 27.405 | 1.5225 | 3.045 | 0 | 7.6125 | Footings | OK
2026-10-26 | Batulao Parkhomes | MD-01 | 15.6 | Precast Wall Panel | 192.816 | 8.034 | 0 | 16.068 | 64.272 | Wall panels | OK
2026-10-26 | Batulao Parkhomes | MD-02 | 2.9 | Precast Slab / Beam | 35.844 | 1.4935 | 2.987 | 0 | 11.948 | Slabs / beams | OK
2026-10-26 | Calauan (Alora+Amani) | MD-01 | 21.4 | Precast Wall Panel | 264.504 | 11.021 | 0 | 22.042 | 88.168 | Wall panels | OK
2026-10-26 | Calauan (Alora+Amani) | MD-03 | 3.9 | Footing / Ground Slab | 36.855 | 2.0475 | 4.095 | 0 | 10.2375 | Footings | OK
2026-10-26 | Gentri | MD-01 | 10.5 | Precast Wall Panel | 129.78 | 5.4075 | 0 | 10.815 | 43.26 | Wall panels | OK
2026-10-26 | Naic | MD-01 | 31.9 | Precast Wall Panel | 394.284 | 16.4285 | 0 | 32.857 | 131.428 | Wall panels | OK
2026-10-26 | Naic | MD-02 | 6.4 | Precast Slab / Beam | 79.104 | 3.296 | 6.592 | 0 | 26.368 | Slabs / beams | OK
2026-10-26 | The Cove Lipa | MD-01 | 22.4 | Precast Wall Panel | 276.864 | 11.536 | 0 | 23.072 | 92.288 | Wall panels | OK
2026-10-26 | The Cove Lipa | MD-04 | 2 | Lean Concrete / Blinding | 12.6 | 1.05 | 2.1 | 0 | 0 | Lean concrete | OK
2026-10-26 | Sights Bay | MD-01 | 11.7 | Precast Wall Panel | 144.612 | 6.0255 | 0 | 12.051 | 48.204 | Wall panels | OK
2026-10-26 | Batulao Impression | MD-01 | 7 | Precast Wall Panel | 86.52 | 3.605 | 0 | 7.21 | 28.84 | Wall panels | OK
2026-10-26 | Batulao Impression | MD-03 | 2.6 | Footing / Ground Slab | 24.57 | 1.365 | 2.73 | 0 | 6.825 | Footings | OK
2026-10-27 | Batulao Parkhomes | MD-01 | 13.3 | Precast Wall Panel | 164.388 | 6.8495 | 0 | 13.699 | 54.796 | Wall panels | OK
2026-10-27 | Batulao Parkhomes | MD-02 | 2.5 | Precast Slab / Beam | 30.9 | 1.2875 | 2.575 | 0 | 10.3 | Slabs / beams | OK
2026-10-27 | Calauan (Alora+Amani) | MD-01 | 22.9 | Precast Wall Panel | 283.044 | 11.7935 | 0 | 23.587 | 94.348 | Wall panels | OK
2026-10-27 | Calauan (Alora+Amani) | MD-03 | 4.2 | Footing / Ground Slab | 39.69 | 2.205 | 4.41 | 0 | 11.025 | Footings | OK
2026-10-27 | Gentri | MD-01 | 9.5 | Precast Wall Panel | 117.42 | 4.8925 | 0 | 9.785 | 39.14 | Wall panels | OK
2026-10-27 | Naic | MD-01 | 28.1 | Precast Wall Panel | 347.316 | 14.4715 | 0 | 28.943 | 115.772 | Wall panels | OK
2026-10-27 | Naic | MD-02 | 5.6 | Precast Slab / Beam | 69.216 | 2.884 | 5.768 | 0 | 23.072 | Slabs / beams | OK
2026-10-27 | The Cove Lipa | MD-01 | 18.8 | Precast Wall Panel | 232.368 | 9.682 | 0 | 19.364 | 77.456 | Wall panels | OK
2026-10-27 | The Cove Lipa | MD-04 | 1.7 | Lean Concrete / Blinding | 10.71 | 0.8925 | 1.785 | 0 | 0 | Lean concrete | OK
2026-10-27 | Batulao Impression | MD-01 | 7.2 | Precast Wall Panel | 88.992 | 3.708 | 0 | 7.416 | 29.664 | Wall panels | OK
2026-10-27 | Batulao Impression | MD-03 | 2.7 | Footing / Ground Slab | 25.515 | 1.4175 | 2.835 | 0 | 7.0875 | Footings | OK
2026-10-28 | Batulao Parkhomes | MD-01 | 16.9 | Precast Wall Panel | 208.884 | 8.7035 | 0 | 17.407 | 69.628 | Wall panels | OK
2026-10-28 | Batulao Parkhomes | MD-02 | 3.2 | Precast Slab / Beam | 39.552 | 1.648 | 3.296 | 0 | 13.184 | Slabs / beams | OK
2026-10-28 | Calauan (Alora+Amani) | MD-01 | 19.4 | Precast Wall Panel | 239.784 | 9.991 | 0 | 19.982 | 79.928 | Wall panels | OK
2026-10-28 | Calauan (Alora+Amani) | MD-03 | 3.5 | Footing / Ground Slab | 33.075 | 1.8375 | 3.675 | 0 | 9.1875 | Footings | OK
2026-10-28 | Gentri | MD-01 | 11.2 | Precast Wall Panel | 138.432 | 5.768 | 0 | 11.536 | 46.144 | Wall panels | OK
2026-10-28 | Naic | MD-01 | 26.1 | Precast Wall Panel | 322.596 | 13.4415 | 0 | 26.883 | 107.532 | Wall panels | OK
2026-10-28 | Naic | MD-02 | 5.2 | Precast Slab / Beam | 64.272 | 2.678 | 5.356 | 0 | 21.424 | Slabs / beams | OK
2026-10-28 | The Cove Lipa | MD-01 | 19.9 | Precast Wall Panel | 245.964 | 10.2485 | 0 | 20.497 | 81.988 | Wall panels | OK
2026-10-28 | The Cove Lipa | MD-04 | 1.8 | Lean Concrete / Blinding | 11.34 | 0.945 | 1.89 | 0 | 0 | Lean concrete | OK
2026-10-28 | Sights Bay | MD-01 | 10.9 | Precast Wall Panel | 134.724 | 5.6135 | 0 | 11.227 | 44.908 | Wall panels | OK
2026-10-28 | Batulao Impression | MD-01 | 7.5 | Precast Wall Panel | 92.7 | 3.8625 | 0 | 7.725 | 30.9 | Wall panels | OK
2026-10-28 | Batulao Impression | MD-03 | 2.8 | Footing / Ground Slab | 26.46 | 1.47 | 2.94 | 0 | 7.35 | Footings | OK
2026-10-29 | Batulao Parkhomes | MD-01 | 14.2 | Precast Wall Panel | 175.512 | 7.313 | 0 | 14.626 | 58.504 | Wall panels | OK
2026-10-29 | Batulao Parkhomes | MD-02 | 2.7 | Precast Slab / Beam | 33.372 | 1.3905 | 2.781 | 0 | 11.124 | Slabs / beams | OK
2026-10-29 | Calauan (Alora+Amani) | MD-01 | 21.9 | Precast Wall Panel | 270.684 | 11.2785 | 0 | 22.557 | 90.228 | Wall panels | OK
2026-10-29 | Calauan (Alora+Amani) | MD-03 | 4 | Footing / Ground Slab | 37.8 | 2.1 | 4.2 | 0 | 10.5 | Footings | OK
2026-10-29 | Gentri | MD-01 | 11.2 | Precast Wall Panel | 138.432 | 5.768 | 0 | 11.536 | 46.144 | Wall panels | OK
2026-10-29 | Naic | MD-01 | 28.3 | Precast Wall Panel | 349.788 | 14.5745 | 0 | 29.149 | 116.596 | Wall panels | OK
2026-10-29 | Naic | MD-02 | 5.7 | Precast Slab / Beam | 70.452 | 2.9355 | 5.871 | 0 | 23.484 | Slabs / beams | OK
2026-10-29 | The Cove Lipa | MD-01 | 20.6 | Precast Wall Panel | 254.616 | 10.609 | 0 | 21.218 | 84.872 | Wall panels | OK
2026-10-29 | The Cove Lipa | MD-04 | 1.9 | Lean Concrete / Blinding | 11.97 | 0.9975 | 1.995 | 0 | 0 | Lean concrete | OK
2026-10-29 | Batulao Impression | MD-01 | 7.8 | Precast Wall Panel | 96.408 | 4.017 | 0 | 8.034 | 32.136 | Wall panels | OK
2026-10-29 | Batulao Impression | MD-03 | 2.9 | Footing / Ground Slab | 27.405 | 1.5225 | 3.045 | 0 | 7.6125 | Footings | OK
2026-10-30 | Batulao Parkhomes | MD-01 | 16.7 | Precast Wall Panel | 206.412 | 8.6005 | 0 | 17.201 | 68.804 | Wall panels | OK
2026-10-30 | Batulao Parkhomes | MD-02 | 3.1 | Precast Slab / Beam | 38.316 | 1.5965 | 3.193 | 0 | 12.772 | Slabs / beams | OK
2026-10-30 | Calauan (Alora+Amani) | MD-01 | 20.3 | Precast Wall Panel | 250.908 | 10.4545 | 0 | 20.909 | 83.636 | Wall panels | OK
2026-10-30 | Calauan (Alora+Amani) | MD-03 | 3.7 | Footing / Ground Slab | 34.965 | 1.9425 | 3.885 | 0 | 9.7125 | Footings | OK
2026-10-30 | Naic | MD-01 | 30.8 | Precast Wall Panel | 380.688 | 15.862 | 0 | 31.724 | 126.896 | Wall panels | OK
2026-10-30 | Naic | MD-02 | 6.2 | Precast Slab / Beam | 76.632 | 3.193 | 6.386 | 0 | 25.544 | Slabs / beams | OK
2026-10-30 | The Cove Lipa | MD-01 | 22.8 | Precast Wall Panel | 281.808 | 11.742 | 0 | 23.484 | 93.936 | Wall panels | OK
2026-10-30 | The Cove Lipa | MD-04 | 2.1 | Lean Concrete / Blinding | 13.23 | 1.1025 | 2.205 | 0 | 0 | Lean concrete | OK
2026-10-30 | Sights Bay | MD-01 | 12.7 | Precast Wall Panel | 156.972 | 6.5405 | 0 | 13.081 | 52.324 | Wall panels | OK
2026-10-30 | Batulao Impression | MD-01 | 7.8 | Precast Wall Panel | 96.408 | 4.017 | 0 | 8.034 | 32.136 | Wall panels | OK
2026-10-30 | Batulao Impression | MD-03 | 2.9 | Footing / Ground Slab | 27.405 | 1.5225 | 3.045 | 0 | 7.6125 | Footings | OK
2026-10-31 | Batulao Parkhomes | MD-01 | 15.1 | Precast Wall Panel | 186.636 | 7.7765 | 0 | 15.553 | 62.212 | Wall panels | OK
2026-10-31 | Batulao Parkhomes | MD-02 | 2.8 | Precast Slab / Beam | 34.608 | 1.442 | 2.884 | 0 | 11.536 | Slabs / beams | OK
2026-10-31 | Calauan (Alora+Amani) | MD-01 | 18.6 | Precast Wall Panel | 229.896 | 9.579 | 0 | 19.158 | 76.632 | Wall panels | OK
2026-10-31 | Calauan (Alora+Amani) | MD-03 | 3.4 | Footing / Ground Slab | 32.13 | 1.785 | 3.57 | 0 | 8.925 | Footings | OK
2026-10-31 | Gentri | MD-01 | 8.5 | Precast Wall Panel | 105.06 | 4.3775 | 0 | 8.755 | 35.02 | Wall panels | OK
2026-10-31 | Naic | MD-01 | 28.6 | Precast Wall Panel | 353.496 | 14.729 | 0 | 29.458 | 117.832 | Wall panels | OK
2026-10-31 | Naic | MD-02 | 5.7 | Precast Slab / Beam | 70.452 | 2.9355 | 5.871 | 0 | 23.484 | Slabs / beams | OK
2026-10-31 | The Cove Lipa | MD-01 | 22.7 | Precast Wall Panel | 280.572 | 11.6905 | 0 | 23.381 | 93.524 | Wall panels | OK
2026-10-31 | The Cove Lipa | MD-04 | 2.1 | Lean Concrete / Blinding | 13.23 | 1.1025 | 2.205 | 0 | 0 | Lean concrete | OK
2026-10-31 | Sights Bay | MD-01 | 11.3 | Precast Wall Panel | 139.668 | 5.8195 | 0 | 11.639 | 46.556 | Wall panels | OK
2026-10-31 | Batulao Impression | MD-01 | 7.5 | Precast Wall Panel | 92.7 | 3.8625 | 0 | 7.725 | 30.9 | Wall panels | OK
2026-10-31 | Batulao Impression | MD-03 | 2.8 | Footing / Ground Slab | 26.46 | 1.47 | 2.94 | 0 | 7.35 | Footings | OK

## Deliveries
3 · Deliveries — New Stock Added to Current Inventory
One row per delivery receipt. 'Received' is added to stock on its date. 'Scheduled' (ordered, not yet arrived) is not added to stock but is used by the Forecast — change it to Received when it arrives.
Date | Site / Project | Material Code | Material | Quantity | Unit | Status | Supplier | DR / Reference No. | Remarks | Check
2026-10-05 | Example Site | CEM | Cement | 500 | bags | Received | Cement Supplier A | DR-000123 | Example row — 1 truck (20 t)
2026-10-03 | Calauan (Alora+Amani) | SAND | Sand | 64 | m3 | Received | Sand Supplier B | DR-041201 | 4 truckload(s) | OK
2026-10-03 | Naic | G38 | Gravel 3/8" | 192 | m3 | Received | Aggregates Supplier C | DR-041202 | 12 truckload(s) | OK
2026-10-03 | The Cove Lipa | SAND | Sand | 64 | m3 | Received | Sand Supplier B | DR-041203 | 4 truckload(s) | OK
2026-10-05 | Batulao Impression | CEM | Cement | 500 | bags | Received | Cement Supplier A | DR-041204 | 2 truckload(s) | OK
2026-10-05 | Batulao Impression | SAND | Sand | 32 | m3 | Received | Sand Supplier B | DR-041205 | 2 truckload(s) | OK
2026-10-05 | Batulao Impression | G34 | Gravel 3/4" | 32 | m3 | Received | Aggregates Supplier C | DR-041206 | 2 truckload(s) | OK
2026-10-05 | Calauan (Alora+Amani) | CEM | Cement | 1500 | bags | Received | Cement Supplier A | DR-041207 | 6 truckload(s) | OK
2026-10-05 | Calauan (Alora+Amani) | G38 | Gravel 3/8" | 96 | m3 | Received | Aggregates Supplier C | DR-041208 | 6 truckload(s) | OK
2026-10-05 | Sights Bay | SAND | Sand | 32 | m3 | Received | Sand Supplier B | DR-041209 | 2 truckload(s) | OK
2026-10-05 | Sights Bay | G38 | Gravel 3/8" | 64 | m3 | Received | Aggregates Supplier C | DR-041210 | 4 truckload(s) | OK
2026-10-05 | The Cove Lipa | G38 | Gravel 3/8" | 160 | m3 | Received | Aggregates Supplier C | DR-041211 | 10 truckload(s) | OK
2026-10-06 | Batulao Parkhomes | SAND | Sand | 64 | m3 | Received | Sand Supplier B | DR-041212 | 4 truckload(s) | OK
2026-10-06 | Batulao Parkhomes | G38 | Gravel 3/8" | 96 | m3 | Received | Aggregates Supplier C | DR-041213 | 6 truckload(s) | OK
2026-10-06 | Calauan (Alora+Amani) | G34 | Gravel 3/4" | 32 | m3 | Received | Aggregates Supplier C | DR-041214 | 2 truckload(s) | OK
2026-10-06 | Naic | CEM | Cement | 2000 | bags | Received | Cement Supplier A | DR-041215 | 8 truckload(s) | OK
2026-10-06 | Tayabas | G38 | Gravel 3/8" | 16 | m3 | Received | Aggregates Supplier C | DR-041216 | 1 truckload(s) | OK
2026-10-06 | The Cove Lipa | CEM | Cement | 1500 | bags | Received | Cement Supplier A | DR-041217 | 6 truckload(s) | OK
2026-10-07 | Batulao Impression | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041218 | 1 drum(s) x 200 L | OK
2026-10-07 | Batulao Parkhomes | G34 | Gravel 3/4" | 32 | m3 | Received | Aggregates Supplier C | DR-041219 | 2 truckload(s) | OK
2026-10-07 | Batulao Parkhomes | ADM | Admixture | 400 | L | Received | Admixture Supplier D | DR-041220 | 2 drum(s) x 200 L | OK
2026-10-07 | Calauan (Alora+Amani) | ADM | Admixture | 400 | L | Received | Admixture Supplier D | DR-041221 | 2 drum(s) x 200 L | OK
2026-10-07 | Gentri | CEM | Cement | 500 | bags | Received | Cement Supplier A | DR-041222 | 2 truckload(s) | OK
2026-10-07 | Gentri | G38 | Gravel 3/8" | 80 | m3 | Received | Aggregates Supplier C | DR-041223 | 5 truckload(s) | OK
2026-10-07 | Gentri | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041224 | 1 drum(s) x 200 L | OK
2026-10-07 | Naic | SAND | Sand | 144 | m3 | Received | Sand Supplier B | DR-041225 | 9 truckload(s) | OK
2026-10-07 | Naic | G34 | Gravel 3/4" | 32 | m3 | Received | Aggregates Supplier C | DR-041226 | 2 truckload(s) | OK
2026-10-07 | Naic | ADM | Admixture | 600 | L | Received | Admixture Supplier D | DR-041227 | 3 drum(s) x 200 L | OK
2026-10-07 | Sights Bay | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041228 | 1 drum(s) x 200 L | OK
2026-10-07 | The Cove Lipa | ADM | Admixture | 400 | L | Received | Admixture Supplier D | DR-041229 | 2 drum(s) x 200 L | OK
2026-10-08 | Batulao Parkhomes | CEM | Cement | 1250 | bags | Received | Cement Supplier A | DR-041230 | 5 truckload(s) | OK
2026-10-08 | Gentri | SAND | Sand | 32 | m3 | Received | Sand Supplier B | DR-041231 | 2 truckload(s) | OK
2026-10-08 | Naic | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041232 | 1 drum(s) x 200 L | OK
2026-10-08 | Sights Bay | CEM | Cement | 1000 | bags | Received | Cement Supplier A | DR-041233 | 4 truckload(s) | OK
2026-10-09 | Batulao Impression | G38 | Gravel 3/8" | 48 | m3 | Received | Aggregates Supplier C | DR-041234 | 3 truckload(s) | OK
2026-10-09 | Calauan (Alora+Amani) | SAND | Sand | 64 | m3 | Received | Sand Supplier B | DR-041235 | 4 truckload(s) | OK
2026-10-09 | Calauan (Alora+Amani) | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041236 | 1 drum(s) x 200 L | OK
2026-10-09 | The Cove Lipa | SAND | Sand | 64 | m3 | Received | Sand Supplier B | DR-041237 | 4 truckload(s) | OK
2026-10-09 | The Cove Lipa | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041238 | 1 drum(s) x 200 L | OK
2026-10-10 | Batulao Impression | CEM | Cement | 500 | bags | Received | Cement Supplier A | DR-041239 | 2 truckload(s) | OK
2026-10-10 | Calauan (Alora+Amani) | CEM | Cement | 1500 | bags | Received | Cement Supplier A | DR-041240 | 6 truckload(s) | OK
2026-10-10 | Calauan (Alora+Amani) | G38 | Gravel 3/8" | 112 | m3 | Received | Aggregates Supplier C | DR-041241 | 7 truckload(s) | OK
2026-10-10 | Gentri | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041242 | 1 drum(s) x 200 L | OK
2026-10-10 | Naic | CEM | Cement | 1750 | bags | Received | Cement Supplier A | DR-041243 | 7 truckload(s) | OK
2026-10-10 | Naic | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041244 | 1 drum(s) x 200 L | OK
2026-10-10 | Sights Bay | G38 | Gravel 3/8" | 64 | m3 | Received | Aggregates Supplier C | DR-041245 | 4 truckload(s) | OK
2026-10-10 | Sights Bay | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041246 | 1 drum(s) x 200 L | OK
2026-10-12 | Batulao Parkhomes | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041247 | 1 drum(s) x 200 L | OK
2026-10-12 | Calauan (Alora+Amani) | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041248 | 1 drum(s) x 200 L | OK
2026-10-12 | Gentri | CEM | Cement | 500 | bags | Received | Cement Supplier A | DR-041249 | 2 truckload(s) | OK
2026-10-12 | Naic | G38 | Gravel 3/8" | 208 | m3 | Received | Aggregates Supplier C | DR-041250 | 13 truckload(s) | OK
2026-10-12 | Naic | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041251 | 1 drum(s) x 200 L | OK
2026-10-12 | Sights Bay | SAND | Sand | 32 | m3 | Received | Sand Supplier B | DR-041252 | 2 truckload(s) | OK
2026-10-12 | The Cove Lipa | CEM | Cement | 1500 | bags | Received | Cement Supplier A | DR-041253 | 6 truckload(s) | OK
2026-10-13 | Batulao Impression | SAND | Sand | 32 | m3 | Received | Sand Supplier B | DR-041254 | 2 truckload(s) | OK
2026-10-13 | Batulao Parkhomes | G38 | Gravel 3/8" | 112 | m3 | Received | Aggregates Supplier C | DR-041255 | 7 truckload(s) | OK
2026-10-13 | Tayabas | CEM | Cement | 500 | bags | Received | Cement Supplier A | DR-041256 | 2 truckload(s) | OK
2026-10-13 | Tayabas | G38 | Gravel 3/8" | 32 | m3 | Received | Aggregates Supplier C | DR-041257 | 2 truckload(s) | OK
2026-10-13 | The Cove Lipa | G38 | Gravel 3/8" | 160 | m3 | Received | Aggregates Supplier C | DR-041258 | 10 truckload(s) | OK
2026-10-13 | The Cove Lipa | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041259 | 1 drum(s) x 200 L | OK
2026-10-14 | Batulao Parkhomes | CEM | Cement | 1250 | bags | Received | Cement Supplier A | DR-041260 | 5 truckload(s) | OK
2026-10-14 | Batulao Parkhomes | SAND | Sand | 64 | m3 | Received | Sand Supplier B | DR-041261 | 4 truckload(s) | OK
2026-10-14 | Calauan (Alora+Amani) | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041262 | 1 drum(s) x 200 L | OK
2026-10-14 | Naic | G34 | Gravel 3/4" | 48 | m3 | Received | Aggregates Supplier C | DR-041263 | 3 truckload(s) | OK
2026-10-14 | Naic | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041264 | 1 drum(s) x 200 L | OK
2026-10-15 | Batulao Impression | CEM | Cement | 500 | bags | Received | Cement Supplier A | DR-041265 | 2 truckload(s) | OK
2026-10-15 | Batulao Impression | G38 | Gravel 3/8" | 32 | m3 | Received | Aggregates Supplier C | DR-041266 | 2 truckload(s) | OK
2026-10-15 | Batulao Impression | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041267 | 1 drum(s) x 200 L | OK
2026-10-15 | Batulao Parkhomes | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041268 | 1 drum(s) x 200 L | OK
2026-10-15 | Calauan (Alora+Amani) | SAND | Sand | 64 | m3 | Received | Sand Supplier B | DR-041269 | 4 truckload(s) | OK
2026-10-15 | Calauan (Alora+Amani) | G34 | Gravel 3/4" | 32 | m3 | Received | Aggregates Supplier C | DR-041270 | 2 truckload(s) | OK
2026-10-15 | Gentri | SAND | Sand | 32 | m3 | Received | Sand Supplier B | DR-041271 | 2 truckload(s) | OK
2026-10-15 | Naic | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041272 | 1 drum(s) x 200 L | OK
2026-10-15 | Sights Bay | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041273 | 1 drum(s) x 200 L | OK
2026-10-15 | The Cove Lipa | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041274 | 1 drum(s) x 200 L | OK
2026-10-16 | Calauan (Alora+Amani) | CEM | Cement | 1250 | bags | Received | Cement Supplier A | DR-041275 | 5 truckload(s) | OK
2026-10-16 | Calauan (Alora+Amani) | G38 | Gravel 3/8" | 96 | m3 | Received | Aggregates Supplier C | DR-041276 | 6 truckload(s) | OK
2026-10-16 | Calauan (Alora+Amani) | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041277 | 1 drum(s) x 200 L | OK
2026-10-16 | Gentri | CEM | Cement | 500 | bags | Received | Cement Supplier A | DR-041278 | 2 truckload(s) | OK
2026-10-16 | Gentri | G38 | Gravel 3/8" | 80 | m3 | Received | Aggregates Supplier C | DR-041279 | 5 truckload(s) | OK
2026-10-16 | Gentri | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041280 | 1 drum(s) x 200 L | OK
2026-10-16 | Naic | CEM | Cement | 2250 | bags | Received | Cement Supplier A | DR-041281 | 9 truckload(s) | OK
2026-10-16 | Naic | SAND | Sand | 144 | m3 | Received | Sand Supplier B | DR-041282 | 9 truckload(s) | OK
2026-10-16 | Naic | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041283 | 1 drum(s) x 200 L | OK
2026-10-16 | Sights Bay | CEM | Cement | 1000 | bags | Received | Cement Supplier A | DR-041284 | 4 truckload(s) | OK
2026-10-16 | The Cove Lipa | SAND | Sand | 64 | m3 | Received | Sand Supplier B | DR-041285 | 4 truckload(s) | OK
2026-10-17 | Batulao Parkhomes | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041286 | 1 drum(s) x 200 L | OK
2026-10-17 | Sights Bay | SAND | Sand | 32 | m3 | Received | Sand Supplier B | DR-041287 | 2 truckload(s) | OK
2026-10-17 | Sights Bay | G38 | Gravel 3/8" | 64 | m3 | Received | Aggregates Supplier C | DR-041288 | 4 truckload(s) | OK
2026-10-17 | The Cove Lipa | CEM | Cement | 1250 | bags | Received | Cement Supplier A | DR-041289 | 5 truckload(s) | OK
2026-10-17 | The Cove Lipa | G34 | Gravel 3/4" | 32 | m3 | Received | Aggregates Supplier C | DR-041290 | 2 truckload(s) | OK
2026-10-17 | The Cove Lipa | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041291 | 1 drum(s) x 200 L | OK
2026-10-19 | Batulao Impression | G34 | Gravel 3/4" | 32 | m3 | Received | Aggregates Supplier C | DR-041292 | 2 truckload(s) | OK
2026-10-19 | Batulao Parkhomes | G34 | Gravel 3/4" | 32 | m3 | Received | Aggregates Supplier C | DR-041293 | 2 truckload(s) | OK
2026-10-19 | Calauan (Alora+Amani) | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041294 | 1 drum(s) x 200 L | OK
2026-10-19 | Naic | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041295 | 1 drum(s) x 200 L | OK
2026-10-20 | Batulao Impression | CEM | Cement | 500 | bags | Received | Cement Supplier A | DR-041296 | 2 truckload(s) | OK
2026-10-20 | Batulao Impression | SAND | Sand | 32 | m3 | Received | Sand Supplier B | DR-041297 | 2 truckload(s) | OK
2026-10-20 | Batulao Impression | G38 | Gravel 3/8" | 32 | m3 | Received | Aggregates Supplier C | DR-041298 | 2 truckload(s) | OK
2026-10-20 | Batulao Impression | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041299 | 1 drum(s) x 200 L | OK
2026-10-20 | Naic | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041300 | 1 drum(s) x 200 L | OK
2026-10-20 | The Cove Lipa | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041301 | 1 drum(s) x 200 L | OK
2026-10-21 | Batulao Parkhomes | CEM | Cement | 1500 | bags | Received | Cement Supplier A | DR-041302 | 6 truckload(s) | OK
2026-10-21 | Batulao Parkhomes | SAND | Sand | 64 | m3 | Received | Sand Supplier B | DR-041303 | 4 truckload(s) | OK
2026-10-21 | Batulao Parkhomes | G38 | Gravel 3/8" | 112 | m3 | Received | Aggregates Supplier C | DR-041304 | 7 truckload(s) | OK
2026-10-21 | Batulao Parkhomes | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041305 | 1 drum(s) x 200 L | OK
2026-10-21 | Calauan (Alora+Amani) | CEM | Cement | 1250 | bags | Received | Cement Supplier A | DR-041306 | 5 truckload(s) | OK
2026-10-21 | Calauan (Alora+Amani) | SAND | Sand | 64 | m3 | Received | Sand Supplier B | DR-041307 | 4 truckload(s) | OK
2026-10-21 | Calauan (Alora+Amani) | G38 | Gravel 3/8" | 96 | m3 | Received | Aggregates Supplier C | DR-041308 | 6 truckload(s) | OK
2026-10-21 | Calauan (Alora+Amani) | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041309 | 1 drum(s) x 200 L | OK
2026-10-21 | Gentri | CEM | Cement | 500 | bags | Received | Cement Supplier A | DR-041310 | 2 truckload(s) | OK
2026-10-21 | Naic | G38 | Gravel 3/8" | 208 | m3 | Received | Aggregates Supplier C | DR-041311 | 13 truckload(s) | OK
2026-10-21 | Sights Bay | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041312 | 1 drum(s) x 200 L | OK
2026-10-22 | Gentri | SAND | Sand | 32 | m3 | Received | Sand Supplier B | DR-041313 | 2 truckload(s) | OK
2026-10-22 | Gentri | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041314 | 1 drum(s) x 200 L | OK
2026-10-22 | The Cove Lipa | G38 | Gravel 3/8" | 160 | m3 | Received | Aggregates Supplier C | DR-041315 | 10 truckload(s) | OK
2026-10-22 | The Cove Lipa | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041316 | 1 drum(s) x 200 L | OK
2026-10-23 | Calauan (Alora+Amani) | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041317 | 1 drum(s) x 200 L | OK
2026-10-23 | Naic | CEM | Cement | 2000 | bags | Received | Cement Supplier A | DR-041318 | 8 truckload(s) | OK
2026-10-23 | Naic | G34 | Gravel 3/4" | 32 | m3 | Received | Aggregates Supplier C | DR-041319 | 2 truckload(s) | OK
2026-10-23 | Naic | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041320 | 1 drum(s) x 200 L | OK
2026-10-23 | Sights Bay | CEM | Cement | 1000 | bags | Received | Cement Supplier A | DR-041321 | 4 truckload(s) | OK
2026-10-23 | Sights Bay | SAND | Sand | 32 | m3 | Received | Sand Supplier B | DR-041322 | 2 truckload(s) | OK
2026-10-23 | Sights Bay | G38 | Gravel 3/8" | 64 | m3 | Received | Aggregates Supplier C | DR-041323 | 4 truckload(s) | OK
2026-10-23 | The Cove Lipa | SAND | Sand | 64 | m3 | Received | Sand Supplier B | DR-041324 | 4 truckload(s) | OK
2026-10-24 | Batulao Impression | CEM | Cement | 500 | bags | Received | Cement Supplier A | DR-041325 | 2 truckload(s) | OK
2026-10-24 | Batulao Impression | G38 | Gravel 3/8" | 32 | m3 | Received | Aggregates Supplier C | DR-041326 | 2 truckload(s) | OK
2026-10-24 | Batulao Parkhomes | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041327 | 1 drum(s) x 200 L | OK
2026-10-24 | Calauan (Alora+Amani) | G34 | Gravel 3/4" | 32 | m3 | Received | Aggregates Supplier C | DR-041328 | 2 truckload(s) | OK
2026-10-24 | Gentri | G38 | Gravel 3/8" | 64 | m3 | Received | Aggregates Supplier C | DR-041329 | 4 truckload(s) | OK
2026-10-24 | Naic | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041330 | 1 drum(s) x 200 L | OK
2026-10-24 | Sights Bay | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041331 | 1 drum(s) x 200 L | OK
2026-10-24 | Tayabas | G38 | Gravel 3/8" | 32 | m3 | Received | Aggregates Supplier C | DR-041332 | 2 truckload(s) | OK
2026-10-24 | The Cove Lipa | CEM | Cement | 1500 | bags | Received | Cement Supplier A | DR-041333 | 6 truckload(s) | OK
2026-10-26 | Calauan (Alora+Amani) | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041334 | 1 drum(s) x 200 L | OK
2026-10-26 | Gentri | CEM | Cement | 500 | bags | Received | Cement Supplier A | DR-041335 | 2 truckload(s) | OK
2026-10-26 | Naic | SAND | Sand | 128 | m3 | Received | Sand Supplier B | DR-041336 | 8 truckload(s) | OK
2026-10-26 | Naic | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041337 | 1 drum(s) x 200 L | OK
2026-10-27 | Batulao Impression | SAND | Sand | 32 | m3 | Received | Sand Supplier B | DR-041338 | 2 truckload(s) | OK
2026-10-27 | Batulao Impression | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041339 | 1 drum(s) x 200 L | OK
2026-10-27 | Batulao Parkhomes | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041340 | 1 drum(s) x 200 L | OK
2026-10-27 | Calauan (Alora+Amani) | CEM | Cement | 1500 | bags | Received | Cement Supplier A | DR-041341 | 6 truckload(s) | OK
2026-10-28 | Batulao Parkhomes | CEM | Cement | 1250 | bags | Received | Cement Supplier A | DR-041342 | 5 truckload(s) | OK
2026-10-28 | Calauan (Alora+Amani) | SAND | Sand | 64 | m3 | Received | Sand Supplier B | DR-041343 | 4 truckload(s) | OK
2026-10-28 | Calauan (Alora+Amani) | G38 | Gravel 3/8" | 112 | m3 | Received | Aggregates Supplier C | DR-041344 | 7 truckload(s) | OK
2026-10-28 | Gentri | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041345 | 1 drum(s) x 200 L | OK
2026-10-28 | Naic | G38 | Gravel 3/8" | 192 | m3 | Received | Aggregates Supplier C | DR-041346 | 12 truckload(s) | OK
2026-10-28 | Naic | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041347 | 1 drum(s) x 200 L | OK
2026-10-29 | Batulao Impression | G38 | Gravel 3/8" | 32 | m3 | Received | Aggregates Supplier C | DR-041348 | 2 truckload(s) | OK
2026-10-29 | Batulao Parkhomes | SAND | Sand | 64 | m3 | Received | Sand Supplier B | DR-041349 | 4 truckload(s) | OK
2026-10-29 | Batulao Parkhomes | G38 | Gravel 3/8" | 112 | m3 | Received | Aggregates Supplier C | DR-041350 | 7 truckload(s) | OK
2026-10-29 | Calauan (Alora+Amani) | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041351 | 1 drum(s) x 200 L | OK
2026-10-29 | Naic | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041352 | 1 drum(s) x 200 L | OK
2026-10-29 | Sights Bay | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041353 | 1 drum(s) x 200 L | OK
2026-10-30 | Batulao Parkhomes | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041354 | 1 drum(s) x 200 L | OK
2026-10-30 | Naic | G34 | Gravel 3/4" | 48 | m3 | Received | Aggregates Supplier C | DR-041355 | 3 truckload(s) | OK
2026-10-30 | Naic | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041356 | 1 drum(s) x 200 L | OK
2026-10-30 | Sights Bay | SAND | Sand | 32 | m3 | Received | Sand Supplier B | DR-041357 | 2 truckload(s) | OK
2026-10-30 | Sights Bay | G38 | Gravel 3/8" | 64 | m3 | Received | Aggregates Supplier C | DR-041358 | 4 truckload(s) | OK
2026-10-30 | The Cove Lipa | SAND | Sand | 64 | m3 | Received | Sand Supplier B | DR-041359 | 4 truckload(s) | OK
2026-10-31 | Batulao Impression | G34 | Gravel 3/4" | 32 | m3 | Received | Aggregates Supplier C | DR-041360 | 2 truckload(s) | OK
2026-10-31 | Batulao Parkhomes | G34 | Gravel 3/4" | 32 | m3 | Received | Aggregates Supplier C | DR-041361 | 2 truckload(s) | OK
2026-10-31 | Calauan (Alora+Amani) | ADM | Admixture | 200 | L | Received | Admixture Supplier D | DR-041362 | 1 drum(s) x 200 L | OK
2026-10-31 | Gentri | CEM | Cement | 500 | bags | Received | Cement Supplier A | DR-041363 | 2 truckload(s) | OK
2026-10-31 | The Cove Lipa | CEM | Cement | 1250 | bags | Received | Cement Supplier A | DR-041364 | 5 truckload(s) | OK
2026-11-02 | Batulao Impression | ADM | Admixture | 200 | L | Scheduled | Admixture Supplier D | PO pending | 1 drum(s) x 200 L | OK
2026-11-03 | Calauan (Alora+Amani) | SAND | Sand | 64 | m3 | Scheduled | Sand Supplier B | PO pending | 4 truckload(s) | OK
2026-11-03 | Calauan (Alora+Amani) | G34 | Gravel 3/4" | 32 | m3 | Scheduled | Aggregates Supplier C | PO pending | 2 truckload(s) | OK
2026-11-03 | Calauan (Alora+Amani) | G38 | Gravel 3/8" | 112 | m3 | Scheduled | Aggregates Supplier C | PO pending | 7 truckload(s) | OK
2026-11-03 | Calauan (Alora+Amani) | ADM | Admixture | 200 | L | Scheduled | Admixture Supplier D | PO pending | 1 drum(s) x 200 L | OK
2026-11-03 | Gentri | ADM | Admixture | 200 | L | Scheduled | Admixture Supplier D | PO pending | 1 drum(s) x 200 L | OK
2026-11-04 | Batulao Parkhomes | CEM | Cement | 1250 | bags | Scheduled | Cement Supplier A | PO pending | 5 truckload(s) | OK
2026-11-05 | Batulao Impression | SAND | Sand | 32 | m3 | Scheduled | Sand Supplier B | PO pending | 2 truckload(s) – supplier delay | OK
2026-11-05 | Calauan (Alora+Amani) | ADM | Admixture | 200 | L | Scheduled | Admixture Supplier D | PO pending | 1 drum(s) x 200 L | OK
2026-11-05 | Naic | CEM | Cement | 1750 | bags | Scheduled | Cement Supplier A | PO pending | 7 truckload(s) – supplier delay | OK
2026-11-05 | Naic | ADM | Admixture | 200 | L | Scheduled | Admixture Supplier D | PO pending | 1 drum(s) x 200 L – supplier delay | OK
2026-11-05 | Sights Bay | ADM | Admixture | 200 | L | Scheduled | Admixture Supplier D | PO pending | 1 drum(s) x 200 L | OK
2026-11-06 | Naic | ADM | Admixture | 200 | L | Scheduled | Admixture Supplier D | PO pending | 1 drum(s) x 200 L – supplier delay | OK
2026-11-06 | Tayabas | SAND | Sand | 32 | m3 | Scheduled | Sand Supplier B | PO pending | 2 truckload(s) – supplier delay | OK
2026-11-09 | Naic | ADM | Admixture | 200 | L | Scheduled | Admixture Supplier D | PO pending | 1 drum(s) x 200 L – supplier delay | OK
2026-11-10 | Naic | CEM | Cement | 1750 | bags | Scheduled | Cement Supplier A | PO pending | 7 truckload(s) – supplier delay | OK
2026-11-10 | Naic | ADM | Admixture | 200 | L | Scheduled | Admixture Supplier D | PO pending | 1 drum(s) x 200 L – supplier delay | OK

## Stock Monitor
4 · Stock Monitor — Days Remaining & Critical Alerts
Automatic — do not type here. Daily usage = declared m3/day (Production Plan) × mix design; if no plan is declared, the actual average of the last 7 days. Days are working days (Settings).
OK = enough cover · REORDER = cover ≤ lead time + safety stock → order now · CRITICAL = cover ≤ supplier lead time → stock-out before a normal delivery, expedite · OUT OF STOCK = zero stock. Cover counts scheduled deliveries only if they arrive before the stock-out.
ITEM |  |  |  | STOCK |  |  | USAGE RATE (per working day) |  |  |  | ON HAND ONLY |  | SCHEDULED DELIVERIES |  |  |  | LEVELS |  |  | STATUS & ACTION |  |  |  |  | FOR DASHBOARD (auto)
Site / Project | Code | Material | Unit | Current Stock | Max Capacity | % of Capacity | Planned Use / Day | Actual Avg Use / Day (7 days) | Daily Rate Used | Basis | Days Remaining | Stock-out On (no delivery) | On Order (qty) | Next Delivery | Due Before Stock-out (qty) | Planning Cover (days) | Lead Time (days) | Safety Stock (days) | Reorder Point (qty) | Status | Reorder By | Critical On | Suggested Order Qty | Alert / Action | Reorder By (number) | Critical On (number) | Stock-out (number)
Batulao Parkhomes | CEM | Cement | bags | 1401.468 | 2900 | 48.33% | 234.84 | 224.54 | 234.84 | Plan | 5.9678 | 2026-11-07 | 1250 | 2026-11-04 | 1250 | 11.2905 | 3 | 2 | 1174.2 | OK | 2026-11-07 | 2026-11-11 | 0 | OK – next order by Sat 07-Nov; 1,250 bags on order (next 04-Nov). | 46333 | 46337 | 46333
Batulao Parkhomes | SAND | Sand | m3 | 78.8945 | 120 | 65.75% | 9.785 | 9.3558 | 9.785 | Plan | 8.0628 | 2026-11-11 | 0 |  | 0 | 8.0628 | 2 | 2 | 39.14 | OK | 2026-11-05 | 2026-11-09 | 0 | OK – next order by Thu 05-Nov. | 46331 | 46335 | 46337
Batulao Parkhomes | G34 | Gravel 3/4" | m3 | 40.205 | 48 | 83.76% | 3.09 | 2.9527 | 3.09 | Plan | 13.0113 | 2026-11-17 | 0 |  | 0 | 13.0113 | 2 | 2 | 12.36 | OK | 2026-11-11 | 2026-11-14 | 0 | OK – next order by Wed 11-Nov. | 46337 | 46340 | 46343
Batulao Parkhomes | G38 | Gravel 3/8" | m3 | 134.584 | 200 | 67.29% | 16.48 | 15.759 | 16.48 | Plan | 8.1665 | 2026-11-11 | 0 |  | 0 | 8.1665 | 2 | 2 | 65.92 | OK | 2026-11-05 | 2026-11-09 | 0 | OK – next order by Thu 05-Nov. | 46331 | 46335 | 46337
Batulao Parkhomes | ADM | Admixture | L | 447.156 | 1000 | 44.72% | 78.28 | 74.8467 | 78.28 | Plan | 5.7123 | 2026-11-07 | 0 |  | 0 | 5.7123 | 5 | 3 | 626.24 | REORDER | NOW | 2026-11-02 | 945 | Order now (about 945 L) – becomes critical Mon 02-Nov. | 46326 | 46328 | 46333
Calauan (Alora+Amani) | CEM | Cement | bags | 1322.638 | 3400 | 38.9% | 309.72 | 292.2225 | 309.72 | Plan | 4.2704 | 2026-11-06 | 0 |  | 0 | 4.2704 | 3 | 2 | 1548.6 | REORDER | NOW | 2026-11-03 | 3007 | Order now (about 3,007 bags) – becomes critical Tue 03-Nov. | 46326 | 46329 | 46332
Calauan (Alora+Amani) | SAND | Sand | m3 | 64.042 | 140 | 45.74% | 13.43 | 12.6725 | 13.43 | Plan | 4.7686 | 2026-11-06 | 64 | 2026-11-03 | 64 | 9.534 | 2 | 2 | 53.72 | OK | 2026-11-06 | 2026-11-10 | 0 | OK – next order by Fri 06-Nov; 64 m3 on order (next 03-Nov). | 46332 | 46336 | 46332
Calauan (Alora+Amani) | G34 | Gravel 3/4" | m3 | 22.79 | 60 | 37.98% | 4.2 | 3.9725 | 4.2 | Plan | 5.4262 | 2026-11-07 | 32 | 2026-11-03 | 32 | 13.0452 | 2 | 2 | 16.8 | OK | 2026-11-11 | 2026-11-14 | 0 | OK – next order by Wed 11-Nov; 32 m3 on order (next 03-Nov). | 46337 | 46340 | 46333
Calauan (Alora+Amani) | G38 | Gravel 3/8" | m3 | 109.294 | 230 | 47.52% | 22.66 | 21.3725 | 22.66 | Plan | 4.8232 | 2026-11-06 | 112 | 2026-11-03 | 112 | 9.7658 | 2 | 2 | 90.64 | OK | 2026-11-06 | 2026-11-10 | 0 | OK – next order by Fri 06-Nov; 112 m3 on order (next 03-Nov). | 46332 | 46336 | 46332
Calauan (Alora+Amani) | ADM | Admixture | L | 640.151 | 1200 | 53.35% | 101.14 | 95.4213 | 101.14 | Plan | 6.3294 | 2026-11-09 | 400 | 2026-11-03 | 400 | 10.2843 | 5 | 3 | 809.12 | OK | 2026-11-03 | 2026-11-07 | 0 | OK – next order by Tue 03-Nov; 400 L on order (next 03-Nov). | 46329 | 46333 | 46335
Gentri | CEM | Cement | bags | 1041.804 | 1400 | 74.41% | 123.6 | 104.854 | 123.6 | Plan | 8.4288 | 2026-11-11 | 0 |  | 0 | 8.4288 | 3 | 2 | 618 | OK | 2026-11-04 | 2026-11-07 | 0 | OK – next order by Wed 04-Nov. | 46330 | 46333 | 46337
Gentri | SAND | Sand | m3 | 18.4085 | 70 | 26.3% | 5.15 | 4.3689 | 5.15 | Plan | 3.5745 | 2026-11-05 | 0 |  | 0 | 3.5745 | 2 | 2 | 20.6 | REORDER | NOW | 2026-11-03 | 62 | Order now (about 62 m3) – becomes critical Tue 03-Nov. | 46326 | 46329 | 46331
Gentri | G38 | Gravel 3/8" | m3 | 57.817 | 130 | 44.47% | 10.3 | 8.7378 | 10.3 | Plan | 5.6133 | 2026-11-07 | 0 |  | 0 | 5.6133 | 2 | 2 | 41.2 | OK | 2026-11-02 | 2026-11-05 | 0 | OK – next order by Mon 02-Nov. | 46328 | 46331 | 46333
Gentri | ADM | Admixture | L | 307.268 | 600 | 51.21% | 41.2 | 34.9513 | 41.2 | Plan | 7.458 | 2026-11-10 | 200 | 2026-11-03 | 200 | 12.3123 | 5 | 3 | 329.6 | OK | 2026-11-05 | 2026-11-10 | 0 | OK – next order by Thu 05-Nov; 200 L on order (next 03-Nov). | 46331 | 46336 | 46336
Naic | CEM | Cement | bags | 133.412 | 4700 | 2.839% | 444.96 | 429.716 | 444.96 | Plan | 0.29983 | 2026-11-02 | 3500 | 2026-11-05 | 0 | 0.29983 | 3 | 2 | 2224.8 | CRITICAL | NOW | NOW | 2402 | URGENT – runs out about Mon 02-Nov, before the next delivery (Thu 05-Nov). Expedite it. | 46326 | 46326 | 46328
Naic | SAND | Sand | m3 | 102.2255 | 240 | 42.59% | 18.54 | 17.9048 | 18.54 | Plan | 5.5138 | 2026-11-07 | 0 |  | 0 | 5.5138 | 2 | 2 | 74.16 | OK | 2026-11-02 | 2026-11-05 | 0 | OK – next order by Mon 02-Nov. | 46328 | 46331 | 46333
Naic | G34 | Gravel 3/4" | m3 | 59.058 | 80 | 73.82% | 6.18 | 5.974 | 6.18 | Plan | 9.5563 | 2026-11-12 | 0 |  | 0 | 9.5563 | 2 | 2 | 24.72 | OK | 2026-11-06 | 2026-11-10 | 0 | OK – next order by Fri 06-Nov. | 46332 | 46336 | 46338
Naic | G38 | Gravel 3/8" | m3 | 212.393 | 370 | 57.4% | 30.9 | 29.8357 | 30.9 | Plan | 6.8736 | 2026-11-09 | 0 |  | 0 | 6.8736 | 2 | 2 | 123.6 | OK | 2026-11-03 | 2026-11-06 | 0 | OK – next order by Tue 03-Nov. | 46329 | 46332 | 46335
Naic | ADM | Admixture | L | 707.804 | 1600 | 44.24% | 148.32 | 143.2387 | 148.32 | Plan | 4.7721 | 2026-11-06 | 800 | 2026-11-05 | 400 | 10.1659 | 5 | 3 | 1186.56 | OK | 2026-11-03 | 2026-11-07 | 0 | OK – next order by Tue 03-Nov; 800 L on order (next 05-Nov). | 46329 | 46333 | 46332
The Cove Lipa | CEM | Cement | bags | 2168.948 | 3200 | 67.78% | 284.52 | 274.212 | 284.52 | Plan | 7.6232 | 2026-11-10 | 0 |  | 0 | 7.6232 | 3 | 2 | 1422.6 | OK | 2026-11-03 | 2026-11-06 | 0 | OK – next order by Tue 03-Nov. | 46329 | 46332 | 46336
The Cove Lipa | SAND | Sand | m3 | 89.9795 | 130 | 69.22% | 12.38 | 11.933 | 12.38 | Plan | 7.2681 | 2026-11-10 | 0 |  | 0 | 7.2681 | 2 | 2 | 49.52 | OK | 2026-11-04 | 2026-11-07 | 0 | OK – next order by Wed 04-Nov. | 46330 | 46333 | 46336
The Cove Lipa | G34 | Gravel 3/4" | m3 | 16.76 | 48 | 34.92% | 2.1 | 2.03 | 2.1 | Plan | 7.981 | 2026-11-10 | 0 |  | 0 | 7.981 | 2 | 2 | 8.4 | OK | 2026-11-04 | 2026-11-07 | 0 | OK – next order by Wed 04-Nov. | 46330 | 46333 | 46336
The Cove Lipa | G38 | Gravel 3/8" | m3 | 72.199 | 280 | 25.79% | 22.66 | 21.836 | 22.66 | Plan | 3.1862 | 2026-11-05 | 0 |  | 0 | 3.1862 | 2 | 2 | 90.64 | REORDER | NOW | 2026-11-03 | 254 | Order now (about 254 m3) – becomes critical Tue 03-Nov. | 46326 | 46329 | 46331
The Cove Lipa | ADM | Admixture | L | 78.796 | 1100 | 7.163% | 90.64 | 87.344 | 90.64 | Plan | 0.86933 | 2026-11-02 | 0 |  | 0 | 0.86933 | 5 | 3 | 725.12 | CRITICAL | NOW | NOW | 1100 | URGENT – runs out about Mon 02-Nov; a normal order takes 5 days. Order and expedite now. | 46326 | 46326 | 46328
Sights Bay | CEM | Cement | bags | 749.752 | 2000 | 37.49% | 148.32 | 95.996 | 148.32 | Plan | 5.055 | 2026-11-07 | 0 |  | 0 | 5.055 | 3 | 2 | 741.6 | OK | 2026-10-31 | 2026-11-04 | 0 | OK – next order by Sat 31-Oct. | 46326 | 46330 | 46333
Sights Bay | SAND | Sand | m3 | 50.573 | 70 | 72.25% | 6.18 | 3.9998 | 6.18 | Plan | 8.1833 | 2026-11-11 | 0 |  | 0 | 8.1833 | 2 | 2 | 24.72 | OK | 2026-11-05 | 2026-11-09 | 0 | OK – next order by Thu 05-Nov. | 46331 | 46335 | 46337
Sights Bay | G38 | Gravel 3/8" | m3 | 98.146 | 130 | 75.5% | 12.36 | 7.9997 | 12.36 | Plan | 7.9406 | 2026-11-10 | 0 |  | 0 | 7.9406 | 2 | 2 | 49.44 | OK | 2026-11-04 | 2026-11-07 | 0 | OK – next order by Wed 04-Nov. | 46330 | 46333 | 46336
Sights Bay | ADM | Admixture | L | 416.584 | 700 | 59.51% | 49.44 | 31.9987 | 49.44 | Plan | 8.4261 | 2026-11-11 | 200 | 2026-11-05 | 200 | 12.4714 | 5 | 3 | 395.52 | OK | 2026-11-05 | 2026-11-10 | 0 | OK – next order by Thu 05-Nov; 200 L on order (next 05-Nov). | 46331 | 46336 | 46337
Tayabas | CEM | Cement | bags | 242.444 | 750 | 32.33% | 37.08 | 0 | 37.08 | Plan | 6.5384 | 2026-11-09 | 0 |  | 0 | 6.5384 | 3 | 2 | 185.4 | OK | 2026-11-02 | 2026-11-05 | 0 | OK – next order by Mon 02-Nov. | 46328 | 46331 | 46335
Tayabas | SAND | Sand | m3 | 0 | 48 | 0% | 1.545 | 0 | 1.545 | Plan | 0 | OUT | 32 | 2026-11-06 | 0 | 0 | 2 | 2 | 6.18 | OUT OF STOCK | NOW | NOW | 20 | Out of stock – production at risk. Next delivery Fri 06-Nov: expedite it. | 46326 | 46326 | 46326
Tayabas | G38 | Gravel 3/8" | m3 | 42.037 | 48 | 87.58% | 3.09 | 0 | 3.09 | Plan | 13.6042 | 2026-11-17 | 0 |  | 0 | 13.6042 | 2 | 2 | 12.36 | OK | 2026-11-11 | 2026-11-14 | 0 | OK – next order by Wed 11-Nov. | 46337 | 46340 | 46343
Tayabas | ADM | Admixture | L | 204.148 | 600 | 34.02% | 12.36 | 0 | 12.36 | Plan | 16.5168 | 2026-11-20 | 0 |  | 0 | 16.5168 | 5 | 3 | 98.88 | OK | 2026-11-10 | 2026-11-14 | 0 | OK – next order by Tue 10-Nov. | 46336 | 46340 | 46346
Batulao Impression | CEM | Cement | bags | 227.729 | 1400 | 16.27% | 127.23 | 118.5905 | 127.23 | Plan | 1.7899 | 2026-11-03 | 0 |  | 0 | 1.7899 | 3 | 2 | 636.15 | CRITICAL | NOW | NOW | 1400 | URGENT – runs out about Tue 03-Nov; a normal order takes 3 days. Order and expedite now. | 46326 | 46326 | 46329
Batulao Impression | SAND | Sand | m3 | 27.6135 | 70 | 39.45% | 5.695 | 5.3066 | 5.695 | Plan | 4.8487 | 2026-11-06 | 32 | 2026-11-05 | 32 | 10.4677 | 2 | 2 | 22.78 | OK | 2026-11-07 | 2026-11-11 | 0 | OK – next order by Sat 07-Nov; 32 m3 on order (next 05-Nov). | 46333 | 46337 | 46332
Batulao Impression | G34 | Gravel 3/4" | m3 | 41.665 | 48 | 86.8% | 3.15 | 2.9225 | 3.15 | Plan | 13.227 | 2026-11-17 | 0 |  | 0 | 13.227 | 2 | 2 | 12.6 | OK | 2026-11-11 | 2026-11-14 | 0 | OK – next order by Wed 11-Nov. | 46337 | 46340 | 46343
Batulao Impression | G38 | Gravel 3/8" | m3 | 45.562 | 90 | 50.62% | 8.24 | 7.6907 | 8.24 | Plan | 5.5294 | 2026-11-07 | 0 |  | 0 | 5.5294 | 2 | 2 | 32.96 | OK | 2026-11-02 | 2026-11-05 | 0 | OK – next order by Mon 02-Nov. | 46328 | 46331 | 46333
Batulao Impression | ADM | Admixture | L | 207.4105 | 600 | 34.57% | 40.835 | 38.0689 | 40.835 | Plan | 5.0792 | 2026-11-07 | 200 | 2026-11-02 | 200 | 9.977 | 5 | 3 | 326.68 | OK | 2026-11-02 | 2026-11-06 | 0 | OK – next order by Mon 02-Nov; 200 L on order (next 02-Nov). | 46328 | 46332 | 46333
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
[25 empty] | 1000000000 | 1000000000 | 1000000000
Formulas:
Actual Avg Use / Day (7 days) = IF([ITEM]="","",IFERROR(SUMIFS(INDEX(Con_Use,0,MATCH([Code],Mat_Code,0)),Con_Site,[ITEM],Con_Date,">"&(AsOfDate-7),Con_Date,"<="&AsOfDate)/MAX(1,NETWORKDAYS.INTL(AsOfDate-6,AsOfDate,WeekendMask,Holidays)),0))
Stock-out On (no delivery) = IF(OR([ITEM]="",[ON HAND ONLY]=""),"",IF([STOCK]<=0,"OUT",WORKDAY.INTL(AsOfDate,ROUNDUP([ON HAND ONLY],0),WeekendMask,Holidays)))
Next Delivery = IF(OR([ITEM]="",N([SCHEDULED DELIVERIES])<=0),"",SUMPRODUCT(MIN((Del_Site=[ITEM])*(Del_Mat=[Code])*(Del_Date>AsOfDate)*Del_Date+(1-(Del_Site=[ITEM])*(Del_Mat=[Code])*(Del_Date>AsOfDate))*1000000000)))
Reorder By = IF(OR([ITEM]="",[STATUS & ACTION]="NO USAGE"),"",IF(OR([STATUS & ACTION]="OUT OF STOCK",[Planning Cover (days)]<=[LEVELS]+[Safety Stock (days)]),"NOW",WORKDAY.INTL(AsOfDate,INT([Planning Cover (days)]-[LEVELS]-[Safety Stock (days)]),WeekendMask,Holidays)))
Critical On = IF(OR([ITEM]="",[STATUS & ACTION]="NO USAGE"),"",IF(OR([STATUS & ACTION]="OUT OF STOCK",[Planning Cover (days)]<=[LEVELS]),"NOW",WORKDAY.INTL(AsOfDate,ROUNDUP([Planning Cover (days)]-[LEVELS],0),WeekendMask,Holidays)))

## Production Plan
5 · Production Plan — Declared m3 per Day (forecast basis)
One row per site and mix design. Enter the planned concrete volume per working day; weekly and monthly volumes and material requirements are calculated.
|  |  | DECLARED PRODUCTION |  |  | DAILY MATERIAL NEED (incl. allowance) |  |  |  |  | MONTHLY MATERIAL NEED
Site / Project | Mix Code | Mix Description | Planned m3 / Day | m3 / Week | m3 / Month | Cement / day (bags) | Sand / day (m3) | Gravel 3/4" / day (m3) | Gravel 3/8" / day (m3) | Admixture / day (L) | Cement / month (bags) | Sand / month (m3) | Gravel 3/4" / month (m3) | Gravel 3/8" / month (m3) | Admixture / month (L) | Remarks | Check
Example Site | MD-01 | Precast Wall Panel | 20 | (auto) | (auto) | (auto) | (auto) | (auto) | (auto) | (auto) | (auto) | (auto) | (auto) | (auto) | (auto) | Example row — panels, 2 casting beds
Batulao Parkhomes | MD-01 | Precast Wall Panel | 16 | 96 | 416 | 197.76 | 8.24 | 0 | 16.48 | 65.92 | 5141.76 | 214.24 | 0 | 428.48 | 1713.92 | Sample plan | OK
Batulao Parkhomes | MD-02 | Precast Slab / Beam | 3 | 18 | 78 | 37.08 | 1.545 | 3.09 | 0 | 12.36 | 964.08 | 40.17 | 80.34 | 0 | 321.36 | Sample plan | OK
Calauan (Alora+Amani) | MD-01 | Precast Wall Panel | 22 | 132 | 572 | 271.92 | 11.33 | 0 | 22.66 | 90.64 | 7069.92 | 294.58 | 0 | 589.16 | 2356.64 | Sample plan | OK
Calauan (Alora+Amani) | MD-03 | Footing / Ground Slab | 4 | 24 | 104 | 37.8 | 2.1 | 4.2 | 0 | 10.5 | 982.8 | 54.6 | 109.2 | 0 | 273 | Sample plan | OK
Gentri | MD-01 | Precast Wall Panel | 10 | 60 | 260 | 123.6 | 5.15 | 0 | 10.3 | 41.2 | 3213.6 | 133.9 | 0 | 267.8 | 1071.2 | Sample plan | OK
Naic | MD-01 | Precast Wall Panel | 30 | 180 | 780 | 370.8 | 15.45 | 0 | 30.9 | 123.6 | 9640.8 | 401.7 | 0 | 803.4 | 3213.6 | Sample plan | OK
Naic | MD-02 | Precast Slab / Beam | 6 | 36 | 156 | 74.16 | 3.09 | 6.18 | 0 | 24.72 | 1928.16 | 80.34 | 160.68 | 0 | 642.72 | Sample plan | OK
The Cove Lipa | MD-01 | Precast Wall Panel | 22 | 132 | 572 | 271.92 | 11.33 | 0 | 22.66 | 90.64 | 7069.92 | 294.58 | 0 | 589.16 | 2356.64 | Sample plan | OK
The Cove Lipa | MD-04 | Lean Concrete / Blinding | 2 | 12 | 52 | 12.6 | 1.05 | 2.1 | 0 | 0 | 327.6 | 27.3 | 54.6 | 0 | 0 | Sample plan | OK
Sights Bay | MD-01 | Precast Wall Panel | 12 | 72 | 312 | 148.32 | 6.18 | 0 | 12.36 | 49.44 | 3856.32 | 160.68 | 0 | 321.36 | 1285.44 | Sample plan | OK
Tayabas | MD-01 | Precast Wall Panel | 3 | 18 | 78 | 37.08 | 1.545 | 0 | 3.09 | 12.36 | 964.08 | 40.17 | 0 | 80.34 | 321.36 | Sample plan | OK
Batulao Impression | MD-01 | Precast Wall Panel | 8 | 48 | 208 | 98.88 | 4.12 | 0 | 8.24 | 32.96 | 2570.88 | 107.12 | 0 | 214.24 | 856.96 | Sample plan | OK
Batulao Impression | MD-03 | Footing / Ground Slab | 3 | 18 | 78 | 28.35 | 1.575 | 3.15 | 0 | 7.875 | 737.1 | 40.95 | 81.9 | 0 | 204.75 | Sample plan | OK

## Forecast
5 · Forecast — Consumption (Daily → Weekly → Monthly) & 6-Month Stock Projection
Automatic. Usage = declared m3/day (Production Plan) × mix design × working days. Period 1 runs from the day after the As-of Date to month-end; projected stock adds the deliveries dated in each period.
FORECAST PERIODS
Period | P1 | P2 | P3 | P4 | P5 | P6
Start date | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01
End date | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30
Working days | 25 | 27 | 26 | 24 | 27 | 26 | ← actual working days in each period (non-working weekdays and holidays from Settings are skipped)
Label | Nov 2026 | Dec 2026 | Jan 2027 | Feb 2027 | Mar 2027 | Apr 2027
A. CONCRETE PRODUCTION FORECAST (m3) — from the declared m3/day in the Production Plan
Site / Project | Planned m3 / Day | m3 / Week | m3 / Month (full month) | Nov 2026 | Dec 2026 | Jan 2027 | Feb 2027 | Mar 2027 | Apr 2027 | Total next 6 periods
Batulao Parkhomes | 19 | 114 | 494 | 475 | 513 | 494 | 456 | 513 | 494 | 2945
Calauan (Alora+Amani) | 26 | 156 | 676 | 650 | 702 | 676 | 624 | 702 | 676 | 4030
Gentri | 10 | 60 | 260 | 250 | 270 | 260 | 240 | 270 | 260 | 1550
Naic | 36 | 216 | 936 | 900 | 972 | 936 | 864 | 972 | 936 | 5580
The Cove Lipa | 24 | 144 | 624 | 600 | 648 | 624 | 576 | 648 | 624 | 3720
Sights Bay | 12 | 72 | 312 | 300 | 324 | 312 | 288 | 324 | 312 | 1860
Tayabas | 3 | 18 | 78 | 75 | 81 | 78 | 72 | 81 | 78 | 465
Batulao Impression | 11 | 66 | 286 | 275 | 297 | 286 | 264 | 297 | 286 | 1705
TOTAL — ALL SITES | 141 | 846 | 3666 | 3525 | 3807 | 3666 | 3384 | 3807 | 3666 | 21855
B. MATERIAL FORECAST & PROCUREMENT PLAN (per site and material)
ITEM |  |  |  | USAGE RATE, STOCK & TARGET |  |  |  |  | FORECAST CONSUMPTION per period | [5 empty] | SCHEDULED DELIVERIES per period | [5 empty] | STILL TO ORDER per period (keeps stock at the reorder level) | [5 empty] | PROJECTED CLOSING STOCK (with those orders) | [5 empty] | OUTLOOK
Site / Project | Code | Material | Unit | Use / Day | Use / Week | Use / Month (generic) | Current Stock | Target Stock (reorder level) | Nov 2026 | Dec 2026 | Jan 2027 | Feb 2027 | Mar 2027 | Apr 2027 | Nov 2026 | Dec 2026 | Jan 2027 | Feb 2027 | Mar 2027 | Apr 2027 | Nov 2026 | Dec 2026 | Jan 2027 | Feb 2027 | Mar 2027 | Apr 2027 | Nov 2026 | Dec 2026 | Jan 2027 | Feb 2027 | Mar 2027 | Apr 2027 | Runs Out (no new orders) | 6-Period Requirement | Total Still to Order
Batulao Parkhomes | CEM | Cement | bags | 234.84 | 1409.04 | 6105.84 | 1401.468 | 1174.2 | 5871 | 6340.68 | 6105.84 | 5636.16 | 6340.68 | 6105.84 | 1250 | 0 | 0 | 0 | 0 | 0 | 4393.732 | 6340.68 | 6105.84 | 5636.16 | 6340.68 | 6105.84 | 1174.2 | 1174.2 | 1174.2 | 1174.2 | 1174.2 | 1174.2 | Nov 2026 | 36400.2 | 34922.932
Batulao Parkhomes | SAND | Sand | m3 | 9.785 | 58.71 | 254.41 | 78.8945 | 39.14 | 244.625 | 264.195 | 254.41 | 234.84 | 264.195 | 254.41 | 0 | 0 | 0 | 0 | 0 | 0 | 204.8705 | 264.195 | 254.41 | 234.84 | 264.195 | 254.41 | 39.14 | 39.14 | 39.14 | 39.14 | 39.14 | 39.14 | Nov 2026 | 1516.675 | 1476.9205
Batulao Parkhomes | G34 | Gravel 3/4" | m3 | 3.09 | 18.54 | 80.34 | 40.205 | 12.36 | 77.25 | 83.43 | 80.34 | 74.16 | 83.43 | 80.34 | 0 | 0 | 0 | 0 | 0 | 0 | 49.405 | 83.43 | 80.34 | 74.16 | 83.43 | 80.34 | 12.36 | 12.36 | 12.36 | 12.36 | 12.36 | 12.36 | Nov 2026 | 478.95 | 451.105
Batulao Parkhomes | G38 | Gravel 3/8" | m3 | 16.48 | 98.88 | 428.48 | 134.584 | 65.92 | 412 | 444.96 | 428.48 | 395.52 | 444.96 | 428.48 | 0 | 0 | 0 | 0 | 0 | 0 | 343.336 | 444.96 | 428.48 | 395.52 | 444.96 | 428.48 | 65.92 | 65.92 | 65.92 | 65.92 | 65.92 | 65.92 | Nov 2026 | 2554.4 | 2485.736
Batulao Parkhomes | ADM | Admixture | L | 78.28 | 469.68 | 2035.28 | 447.156 | 626.24 | 1957 | 2113.56 | 2035.28 | 1878.72 | 2113.56 | 2035.28 | 0 | 0 | 0 | 0 | 0 | 0 | 2136.084 | 2113.56 | 2035.28 | 1878.72 | 2113.56 | 2035.28 | 626.24 | 626.24 | 626.24 | 626.24 | 626.24 | 626.24 | Nov 2026 | 12133.4 | 12312.484
Calauan (Alora+Amani) | CEM | Cement | bags | 309.72 | 1858.32 | 8052.72 | 1322.638 | 1548.6 | 7743 | 8362.44 | 8052.72 | 7433.28 | 8362.44 | 8052.72 | 0 | 0 | 0 | 0 | 0 | 0 | 7968.962 | 8362.44 | 8052.72 | 7433.28 | 8362.44 | 8052.72 | 1548.6 | 1548.6 | 1548.6 | 1548.6 | 1548.6 | 1548.6 | Nov 2026 | 48006.6 | 48232.562
Calauan (Alora+Amani) | SAND | Sand | m3 | 13.43 | 80.58 | 349.18 | 64.042 | 53.72 | 335.75 | 362.61 | 349.18 | 322.32 | 362.61 | 349.18 | 64 | 0 | 0 | 0 | 0 | 0 | 261.428 | 362.61 | 349.18 | 322.32 | 362.61 | 349.18 | 53.72 | 53.72 | 53.72 | 53.72 | 53.72 | 53.72 | Nov 2026 | 2081.65 | 2007.328
Calauan (Alora+Amani) | G34 | Gravel 3/4" | m3 | 4.2 | 25.2 | 109.2 | 22.79 | 16.8 | 105 | 113.4 | 109.2 | 100.8 | 113.4 | 109.2 | 32 | 0 | 0 | 0 | 0 | 0 | 67.01 | 113.4 | 109.2 | 100.8 | 113.4 | 109.2 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | Nov 2026 | 651 | 613.01
Calauan (Alora+Amani) | G38 | Gravel 3/8" | m3 | 22.66 | 135.96 | 589.16 | 109.294 | 90.64 | 566.5 | 611.82 | 589.16 | 543.84 | 611.82 | 589.16 | 112 | 0 | 0 | 0 | 0 | 0 | 435.846 | 611.82 | 589.16 | 543.84 | 611.82 | 589.16 | 90.64 | 90.64 | 90.64 | 90.64 | 90.64 | 90.64 | Nov 2026 | 3512.3 | 3381.646
Calauan (Alora+Amani) | ADM | Admixture | L | 101.14 | 606.84 | 2629.64 | 640.151 | 809.12 | 2528.5 | 2730.78 | 2629.64 | 2427.36 | 2730.78 | 2629.64 | 400 | 0 | 0 | 0 | 0 | 0 | 2297.469 | 2730.78 | 2629.64 | 2427.36 | 2730.78 | 2629.64 | 809.12 | 809.12 | 809.12 | 809.12 | 809.12 | 809.12 | Nov 2026 | 15676.7 | 15445.669
Gentri | CEM | Cement | bags | 123.6 | 741.6 | 3213.6 | 1041.804 | 618 | 3090 | 3337.2 | 3213.6 | 2966.4 | 3337.2 | 3213.6 | 0 | 0 | 0 | 0 | 0 | 0 | 2666.196 | 3337.2 | 3213.6 | 2966.4 | 3337.2 | 3213.6 | 618 | 618 | 618 | 618 | 618 | 618 | Nov 2026 | 19158 | 18734.196
Gentri | SAND | Sand | m3 | 5.15 | 30.9 | 133.9 | 18.4085 | 20.6 | 128.75 | 139.05 | 133.9 | 123.6 | 139.05 | 133.9 | 0 | 0 | 0 | 0 | 0 | 0 | 130.9415 | 139.05 | 133.9 | 123.6 | 139.05 | 133.9 | 20.6 | 20.6 | 20.6 | 20.6 | 20.6 | 20.6 | Nov 2026 | 798.25 | 800.4415
Gentri | G38 | Gravel 3/8" | m3 | 10.3 | 61.8 | 267.8 | 57.817 | 41.2 | 257.5 | 278.1 | 267.8 | 247.2 | 278.1 | 267.8 | 0 | 0 | 0 | 0 | 0 | 0 | 240.883 | 278.1 | 267.8 | 247.2 | 278.1 | 267.8 | 41.2 | 41.2 | 41.2 | 41.2 | 41.2 | 41.2 | Nov 2026 | 1596.5 | 1579.883
Gentri | ADM | Admixture | L | 41.2 | 247.2 | 1071.2 | 307.268 | 329.6 | 1030 | 1112.4 | 1071.2 | 988.8 | 1112.4 | 1071.2 | 200 | 0 | 0 | 0 | 0 | 0 | 852.332 | 1112.4 | 1071.2 | 988.8 | 1112.4 | 1071.2 | 329.6 | 329.6 | 329.6 | 329.6 | 329.6 | 329.6 | Nov 2026 | 6386 | 6208.332
Naic | CEM | Cement | bags | 444.96 | 2669.76 | 11568.96 | 133.412 | 2224.8 | 11124 | 12013.92 | 11568.96 | 10679.04 | 12013.92 | 11568.96 | 3500 | 0 | 0 | 0 | 0 | 0 | 9715.388 | 12013.92 | 11568.96 | 10679.04 | 12013.92 | 11568.96 | 2224.8 | 2224.8 | 2224.8 | 2224.8 | 2224.8 | 2224.8 | Nov 2026 | 68968.8 | 67560.188
Naic | SAND | Sand | m3 | 18.54 | 111.24 | 482.04 | 102.2255 | 74.16 | 463.5 | 500.58 | 482.04 | 444.96 | 500.58 | 482.04 | 0 | 0 | 0 | 0 | 0 | 0 | 435.4345 | 500.58 | 482.04 | 444.96 | 500.58 | 482.04 | 74.16 | 74.16 | 74.16 | 74.16 | 74.16 | 74.16 | Nov 2026 | 2873.7 | 2845.6345
Naic | G34 | Gravel 3/4" | m3 | 6.18 | 37.08 | 160.68 | 59.058 | 24.72 | 154.5 | 166.86 | 160.68 | 148.32 | 166.86 | 160.68 | 0 | 0 | 0 | 0 | 0 | 0 | 120.162 | 166.86 | 160.68 | 148.32 | 166.86 | 160.68 | 24.72 | 24.72 | 24.72 | 24.72 | 24.72 | 24.72 | Nov 2026 | 957.9 | 923.562
Naic | G38 | Gravel 3/8" | m3 | 30.9 | 185.4 | 803.4 | 212.393 | 123.6 | 772.5 | 834.3 | 803.4 | 741.6 | 834.3 | 803.4 | 0 | 0 | 0 | 0 | 0 | 0 | 683.707 | 834.3 | 803.4 | 741.6 | 834.3 | 803.4 | 123.6 | 123.6 | 123.6 | 123.6 | 123.6 | 123.6 | Nov 2026 | 4789.5 | 4700.707
Naic | ADM | Admixture | L | 148.32 | 889.92 | 3856.32 | 707.804 | 1186.56 | 3708 | 4004.64 | 3856.32 | 3559.68 | 4004.64 | 3856.32 | 800 | 0 | 0 | 0 | 0 | 0 | 3386.756 | 4004.64 | 3856.32 | 3559.68 | 4004.64 | 3856.32 | 1186.56 | 1186.56 | 1186.56 | 1186.56 | 1186.56 | 1186.56 | Nov 2026 | 22989.6 | 22668.356
The Cove Lipa | CEM | Cement | bags | 284.52 | 1707.12 | 7397.52 | 2168.948 | 1422.6 | 7113 | 7682.04 | 7397.52 | 6828.48 | 7682.04 | 7397.52 | 0 | 0 | 0 | 0 | 0 | 0 | 6366.652 | 7682.04 | 7397.52 | 6828.48 | 7682.04 | 7397.52 | 1422.6 | 1422.6 | 1422.6 | 1422.6 | 1422.6 | 1422.6 | Nov 2026 | 44100.6 | 43354.252
The Cove Lipa | SAND | Sand | m3 | 12.38 | 74.28 | 321.88 | 89.9795 | 49.52 | 309.5 | 334.26 | 321.88 | 297.12 | 334.26 | 321.88 | 0 | 0 | 0 | 0 | 0 | 0 | 269.0405 | 334.26 | 321.88 | 297.12 | 334.26 | 321.88 | 49.52 | 49.52 | 49.52 | 49.52 | 49.52 | 49.52 | Nov 2026 | 1918.9 | 1878.4405
The Cove Lipa | G34 | Gravel 3/4" | m3 | 2.1 | 12.6 | 54.6 | 16.76 | 8.4 | 52.5 | 56.7 | 54.6 | 50.4 | 56.7 | 54.6 | 0 | 0 | 0 | 0 | 0 | 0 | 44.14 | 56.7 | 54.6 | 50.4 | 56.7 | 54.6 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | Nov 2026 | 325.5 | 317.14
The Cove Lipa | G38 | Gravel 3/8" | m3 | 22.66 | 135.96 | 589.16 | 72.199 | 90.64 | 566.5 | 611.82 | 589.16 | 543.84 | 611.82 | 589.16 | 0 | 0 | 0 | 0 | 0 | 0 | 584.941 | 611.82 | 589.16 | 543.84 | 611.82 | 589.16 | 90.64 | 90.64 | 90.64 | 90.64 | 90.64 | 90.64 | Nov 2026 | 3512.3 | 3530.741
The Cove Lipa | ADM | Admixture | L | 90.64 | 543.84 | 2356.64 | 78.796 | 725.12 | 2266 | 2447.28 | 2356.64 | 2175.36 | 2447.28 | 2356.64 | 0 | 0 | 0 | 0 | 0 | 0 | 2912.324 | 2447.28 | 2356.64 | 2175.36 | 2447.28 | 2356.64 | 725.12 | 725.12 | 725.12 | 725.12 | 725.12 | 725.12 | Nov 2026 | 14049.2 | 14695.524
Sights Bay | CEM | Cement | bags | 148.32 | 889.92 | 3856.32 | 749.752 | 741.6 | 3708 | 4004.64 | 3856.32 | 3559.68 | 4004.64 | 3856.32 | 0 | 0 | 0 | 0 | 0 | 0 | 3699.848 | 4004.64 | 3856.32 | 3559.68 | 4004.64 | 3856.32 | 741.6 | 741.6 | 741.6 | 741.6 | 741.6 | 741.6 | Nov 2026 | 22989.6 | 22981.448
Sights Bay | SAND | Sand | m3 | 6.18 | 37.08 | 160.68 | 50.573 | 24.72 | 154.5 | 166.86 | 160.68 | 148.32 | 166.86 | 160.68 | 0 | 0 | 0 | 0 | 0 | 0 | 128.647 | 166.86 | 160.68 | 148.32 | 166.86 | 160.68 | 24.72 | 24.72 | 24.72 | 24.72 | 24.72 | 24.72 | Nov 2026 | 957.9 | 932.047
Sights Bay | G38 | Gravel 3/8" | m3 | 12.36 | 74.16 | 321.36 | 98.146 | 49.44 | 309 | 333.72 | 321.36 | 296.64 | 333.72 | 321.36 | 0 | 0 | 0 | 0 | 0 | 0 | 260.294 | 333.72 | 321.36 | 296.64 | 333.72 | 321.36 | 49.44 | 49.44 | 49.44 | 49.44 | 49.44 | 49.44 | Nov 2026 | 1915.8 | 1867.094
Sights Bay | ADM | Admixture | L | 49.44 | 296.64 | 1285.44 | 416.584 | 395.52 | 1236 | 1334.88 | 1285.44 | 1186.56 | 1334.88 | 1285.44 | 200 | 0 | 0 | 0 | 0 | 0 | 1014.936 | 1334.88 | 1285.44 | 1186.56 | 1334.88 | 1285.44 | 395.52 | 395.52 | 395.52 | 395.52 | 395.52 | 395.52 | Nov 2026 | 7663.2 | 7442.136
Tayabas | CEM | Cement | bags | 37.08 | 222.48 | 964.08 | 242.444 | 185.4 | 927 | 1001.16 | 964.08 | 889.92 | 1001.16 | 964.08 | 0 | 0 | 0 | 0 | 0 | 0 | 869.956 | 1001.16 | 964.08 | 889.92 | 1001.16 | 964.08 | 185.4 | 185.4 | 185.4 | 185.4 | 185.4 | 185.4 | Nov 2026 | 5747.4 | 5690.356
Tayabas | SAND | Sand | m3 | 1.545 | 9.27 | 40.17 | 0 | 6.18 | 38.625 | 41.715 | 40.17 | 37.08 | 41.715 | 40.17 | 32 | 0 | 0 | 0 | 0 | 0 | 12.805 | 41.715 | 40.17 | 37.08 | 41.715 | 40.17 | 6.18 | 6.18 | 6.18 | 6.18 | 6.18 | 6.18 | Already out | 239.475 | 213.655
Tayabas | G38 | Gravel 3/8" | m3 | 3.09 | 18.54 | 80.34 | 42.037 | 12.36 | 77.25 | 83.43 | 80.34 | 74.16 | 83.43 | 80.34 | 0 | 0 | 0 | 0 | 0 | 0 | 47.573 | 83.43 | 80.34 | 74.16 | 83.43 | 80.34 | 12.36 | 12.36 | 12.36 | 12.36 | 12.36 | 12.36 | Nov 2026 | 478.95 | 449.273
Tayabas | ADM | Admixture | L | 12.36 | 74.16 | 321.36 | 204.148 | 98.88 | 309 | 333.72 | 321.36 | 296.64 | 333.72 | 321.36 | 0 | 0 | 0 | 0 | 0 | 0 | 203.732 | 333.72 | 321.36 | 296.64 | 333.72 | 321.36 | 98.88 | 98.88 | 98.88 | 98.88 | 98.88 | 98.88 | Nov 2026 | 1915.8 | 1810.532
Batulao Impression | CEM | Cement | bags | 127.23 | 763.38 | 3307.98 | 227.729 | 636.15 | 3180.75 | 3435.21 | 3307.98 | 3053.52 | 3435.21 | 3307.98 | 0 | 0 | 0 | 0 | 0 | 0 | 3589.171 | 3435.21 | 3307.98 | 3053.52 | 3435.21 | 3307.98 | 636.15 | 636.15 | 636.15 | 636.15 | 636.15 | 636.15 | Nov 2026 | 19720.65 | 20129.071
Batulao Impression | SAND | Sand | m3 | 5.695 | 34.17 | 148.07 | 27.6135 | 22.78 | 142.375 | 153.765 | 148.07 | 136.68 | 153.765 | 148.07 | 32 | 0 | 0 | 0 | 0 | 0 | 105.5415 | 153.765 | 148.07 | 136.68 | 153.765 | 148.07 | 22.78 | 22.78 | 22.78 | 22.78 | 22.78 | 22.78 | Nov 2026 | 882.725 | 845.8915
Batulao Impression | G34 | Gravel 3/4" | m3 | 3.15 | 18.9 | 81.9 | 41.665 | 12.6 | 78.75 | 85.05 | 81.9 | 75.6 | 85.05 | 81.9 | 0 | 0 | 0 | 0 | 0 | 0 | 49.685 | 85.05 | 81.9 | 75.6 | 85.05 | 81.9 | 12.6 | 12.6 | 12.6 | 12.6 | 12.6 | 12.6 | Nov 2026 | 488.25 | 459.185
Batulao Impression | G38 | Gravel 3/8" | m3 | 8.24 | 49.44 | 214.24 | 45.562 | 32.96 | 206 | 222.48 | 214.24 | 197.76 | 222.48 | 214.24 | 0 | 0 | 0 | 0 | 0 | 0 | 193.398 | 222.48 | 214.24 | 197.76 | 222.48 | 214.24 | 32.96 | 32.96 | 32.96 | 32.96 | 32.96 | 32.96 | Nov 2026 | 1277.2 | 1264.598
Batulao Impression | ADM | Admixture | L | 40.835 | 245.01 | 1061.71 | 207.4105 | 326.68 | 1020.875 | 1102.545 | 1061.71 | 980.04 | 1102.545 | 1061.71 | 200 | 0 | 0 | 0 | 0 | 0 | 940.1445 | 1102.545 | 1061.71 | 980.04 | 1102.545 | 1061.71 | 326.68 | 326.68 | 326.68 | 326.68 | 326.68 | 326.68 | Nov 2026 | 6329.425 | 6248.6945
Formulas:
P1 = EOMONTH([P1, row above],0)
P1 = NETWORKDAYS.INTL(B6,[P1, row above],WeekendMask,Holidays)
P2 = [P1, row below]+1
P2 = EOMONTH([P2, row above],0)
P3 = [P2, row below]+1
P3 = EOMONTH([P3, row above],0)
P4 = [P3, row below]+1
P4 = EOMONTH([P4, row above],0)
P5 = [P4, row below]+1
P5 = EOMONTH([P5, row above],0)
P6 = [P5, row below]+1
P6 = EOMONTH([P6, row above],0)

## Mix Design
Mix Design — Material Quantity per 1 m3 of Concrete
Fill in the yellow cells with your approved mix design (per 1 m3, in each material's unit: cement in bags, aggregates in m3, admixture in litres). The allowance % covers waste and is added to every m3 produced.
|  |  | QUANTITY PER 1 m3 OF CONCRETE (input) | [6 empty] | USED IN CALCULATIONS — incl. allowance (auto)
Mix Code | Description / Element | Class / Proportion | Cement (bags per m3) | Sand (m3 per m3) | Gravel 3/4" (m3 per m3) | Gravel 3/8" (m3 per m3) | Admixture (L per m3) | Allowance (waste) % | Notes / Source | Cement incl. allowance | Sand incl. allowance | Gravel 3/4" incl. allowance | Gravel 3/8" incl. allowance | Admixture incl. allowance
MD-01 | Precast Wall Panel | Class AA (1 : 1.5 : 3) | 12 | 0.5 | 0 | 1 | 4 | 3% | Typical volumetric proportion per m3 using 40 kg bags (Philippine practice); admixture = typical superplasticizer / water-reducer dosage. Replace with your approved, lab-tested mix design and the supplier's recommended dosage. | 12.36 | 0.515 | 0 | 1.03 | 4.12
MD-02 | Precast Slab / Beam | Class AA (1 : 1.5 : 3) | 12 | 0.5 | 1 | 0 | 4 | 3% | Typical volumetric proportion per m3 using 40 kg bags (Philippine practice); admixture = typical superplasticizer / water-reducer dosage. Replace with your approved, lab-tested mix design and the supplier's recommended dosage. | 12.36 | 0.515 | 1.03 | 0 | 4.12
MD-03 | Footing / Ground Slab | Class A (1 : 2 : 4) | 9 | 0.5 | 1 | 0 | 2.5 | 5% | Typical volumetric proportion per m3 using 40 kg bags (Philippine practice); admixture = typical superplasticizer / water-reducer dosage. Replace with your approved, lab-tested mix design and the supplier's recommended dosage. | 9.45 | 0.525 | 1.05 | 0 | 2.625
MD-04 | Lean Concrete / Blinding | Class C (1 : 3 : 6) | 6 | 0.5 | 1 | 0 | 0 | 5% | Typical volumetric proportion per m3 using 40 kg bags (Philippine practice); admixture = typical superplasticizer / water-reducer dosage. Replace with your approved, lab-tested mix design and the supplier's recommended dosage. | 6.3 | 0.525 | 1.05 | 0 | 0

## Settings
Settings — Report Date, Materials & Sites
Fill in the yellow cells. Material codes (grey) are fixed: Mix Design and log columns follow this order.
GENERAL
As-of Date (report date) | 2026-10-31 | Stock is counted up to and including this date. Keep =TODAY() for live monitoring, or type a date to review a past day.
Working days per week | 6 | Converts working days into calendar dates (6 = Monday to Saturday).
Working days per month | 26 | Used for the generic monthly requirement (daily use × this).
Non-working weekdays (auto) | 0000001 | Monday→Sunday, 1 = no work. 6 days/week = Sunday off; 5 = Saturday and Sunday off. Used to skip non-working days in dates and forecasts.
MATERIALS
# | Code (fixed) | Short Name | Description | Unit | Lead Time (working days) | Safety Stock (working days) | Notes
1 | CEM | Cement | Portland Cement Type 1 (40 kg bag) | bags | 3 | 2 | 1 bag = 40 kg. Lead time = order to delivery on site. Lead time and safety stock are assumptions: confirm with supplier.
2 | SAND | Sand | Fine Aggregate - Washed Sand | m3 | 2 | 2 | Loose volume as delivered (m3).
3 | G34 | Gravel 3/4" | Coarse Aggregate - 3/4" Crushed Gravel | m3 | 2 | 2 | Loose volume as delivered (m3).
4 | G38 | Gravel 3/8" | Coarse Aggregate - 3/8" Crushed Gravel | m3 | 2 | 2 | Loose volume as delivered (m3).
5 | ADM | Admixture | Concrete Admixture - Superplasticizer / Water Reducer | L | 5 | 3 | Liquid, in litres. Delivered in 200 L drums or 1,000 L IBC totes. Lead time and safety stock are assumptions: confirm with supplier.
SITES / PROJECTS
# | Site / Project | Notes
| All Sites | Combined view on the Dashboard — do not change.
1 | Batulao Parkhomes
2 | Calauan (Alora+Amani)
3 | Gentri
4 | Naic
5 | The Cove Lipa
6 | Sights Bay
7 | Tayabas
8 | Batulao Impression
9
10
11
12
13
14
15
16
17
18
19
20
NON-WORKING HOLIDAYS (optional)
# | Date | Holiday / Reason
1 |  |  | Days with no production. They are skipped in stock-out / reorder dates and forecast working days. Left empty = conservative (assumes work continues).
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20