## Instructions
FTB Supply & Production — Data Workbook
This workbook is the data source for the FTB Supply & Production Dashboard.
HOW TO USE
1. Fill in the yellow cells in 'Project Overview' with your current site-level totals.
2. Each month, add a new row to 'Monthly History' with that month's production/installation totals per site.
3. Save this file, then in the dashboard click 'Upload File' and select this workbook (.xlsx).
4. The dashboard reads both tabs automatically — Project Overview for the current snapshot, and Monthly History for the 6-month projection chart.
COLOR LEGEND
Yellow cells = type your data here
Grey cells = calculated automatically — do not type over these
Light grey/italic = example row — delete or ignore, just shows the expected format
PROJECT OVERVIEW — COLUMN NOTES
Contract Units Total units contracted for this site.
With PO Units that currently have an issued Purchase Order.
No PO Auto-calculated: Contract Units minus With PO.
PO % Auto-calculated: With PO ÷ Contract Units.
FTB Produced Cumulative FTB units produced to date.
Installed Cumulative units installed to date.
Deductions Optional. Units to exclude from the buffer (e.g. awarded to another
contractor, or punchlist units already accounted for elsewhere).
Available FTB Auto-calculated: FTB Produced − Installed − Deductions.
COCA Cumulative units that have passed COCA.
Critical Month Your own manual estimate of when this site runs out of buffer (optional —
free text, just for reference alongside the dashboard's own projection).
Risk Level Optional manual override — leave BLANK to let the dashboard calculate it
automatically. If you do set it, use exactly: critical / watch / lower
(watch = At Risk, lower = On Track).
Auto Risk (preview) Read-only — shows what the dashboard will display if Risk Level is left blank.
Notes / Action Free text shown on the dashboard's Priority Risk Board.
MONTHLY HISTORY — COLUMN NOTES
Site Pick from the dropdown (sourced from Project Overview).
Month Format YYYY-MM, e.g. 2026-07 for July 2026.
FTB Produced Units produced THAT MONTH ONLY (not a running total).
Installed Units installed THAT MONTH ONLY (not a running total).
The dashboard uses the most recent 3 months per site to calculate an average monthly rate, then projects forward 6 months to flag when a site is likely to cross the 100-unit critical variance threshold.
RISK METHODOLOGY (calculated automatically by the dashboard)
Critical variance (FTB Produced − Installed) below 100 units
At Risk variance between 100–199 units
On Track variance of 200+ units
PRODUCTION & INSTALLATION EFFICIENCY (NEW)
IMPORTANT: FTB is supplied by the client (Phirst Park Homes) — 'FTB Produced' above tracks their
scope, not ours. The columns below track PCS's own production (panels) and installation activity,
which is a separate scope from FTB.
Available both in Project Overview (cumulative, columns P-W) and Monthly History (columns E-L,
per month) — use whichever view fits how you want to track it.
Manpower (Production) Headcount assigned to panel production.
Manpower (Installation) Headcount assigned to installation.
Manhours (Production) Total hours worked by the production crew. Kept separate from
installation manhours so neither efficiency figure gets distorted
by the other activity's labor.
Manhours (Installation) Total hours worked by the installation crew.
Volume Produced m3 Cubic meters of panels produced by PCS this period.
Volume Installed m3 Cubic meters actually installed this period.
Production Efficiency Auto-calculated: Volume Produced ÷ Manhours (Production).
Measured in m3 per manhour.
Installation Efficiency Auto-calculated: Volume Installed ÷ Manhours (Installation).
Measured in m3 per manhour.
ANNUAL HISTORY (NEW) — PRE-2026 REFERENCE ONLY
For sites that started before monthly tracking began. One row per site per year (2021-2025).
This sheet is NOT read by the dashboard — it's a historical reference only, since annual totals
can't be used for the monthly projection math. The dashboard's projection only uses Monthly
History (2026 onward), which is when your real monthly tracking starts.
MONTHLY HISTORY — TWO NEW COLUMNS ADDED
Target Installation Planned/budgeted installation for that month.
RFIA COCA Request for Inspection/Acceptance this month — the stage before
final COCA clearance. Tracked separately from COCA itself.
MONTHLY HISTORY — PLAN VS. ACTUAL (NEW)
Target FTB Produced Planned/forecast FTB availability from the client for that month.
Compare against actual FTB Produced to catch client-side
delivery delays early. Shown on the dashboard as a Plan vs.
Actual chart, alongside Target Installation vs. Actual Installation.

## Project Overview
FTB Supply & Production — Project Overview
Fill in yellow cells only. Grey cells are auto-calculated — do not overwrite them.
Site | Contract Units | With PO | No PO | PO % | FTB Produced | Installed | Deductions (Punchlist/Awarded/Hold Units) | Available FTB | COCA | Critical Month | Risk Level | Auto Risk (preview) | Notes | Action
Batulao Parkhomes | 2052 | 2019 | 33 | 98.39% | 1839 | 1824 | 0 | 15 | 1685 |  |  | Critical
Calauan (Alora+Amani) | 2220 | 666 | 1554 | 30% | 521 | 416 | 26 | 79 | 316 |  |  | At Risk
Gentri | 1642 | 1540 | 102 | 93.79% | 1379 | 1287 | 0 | 92 | 819 |  |  | Critical
Naic | 1943 | 1685 | 258 | 86.72% | 1218 | 1058 | 0 | 160 | 1026 |  |  | At Risk
The Cove Lipa | 1116 | 1018 | 98 | 91.22% | 844 | 604 | 0 | 240 | 616 |  |  | On Track
Sights Bay | 2266 | 1540 | 726 | 67.96% | 2044 | 1812 | 0 | 232 | 1788 |  |  | On Track
Tayabas | 2048 | 1615 | 433 | 78.86% | 1450 | 1274 | 0 | 176 | 1240 |  |  | At Risk
Batulao Impression | 1054 | 296 | 758 | 28.08% | 184 | 30 | 0 | 154 | 0 |  |  | At Risk
|  |  | 0 | 0% |  |  |  | 0 |  |  |  | Critical
|  |  | 0 | 0% |  |  |  | 0 |  |  |  | Critical
|  |  | 0 | 0% |  |  |  | 0 |  |  |  | Critical
|  |  | 0 | 0% |  |  |  | 0 |  |  |  | Critical
|  |  | 0 | 0% |  |  |  | 0 |  |  |  | Critical
|  |  | 0 | 0% |  |  |  | 0 |  |  |  | Critical
Note on H4: Optional. Use this for units that shouldn't count toward Available FTB — e.g. units awarded to another contractor, or punchlist units already accounted for elsewhere.
Note on L4: Optional manual override. Leave blank to let the dashboard calculate risk automatically from FTB Produced − Installed. If you do fill this in, use exactly one of: critical = Critical watch = At Risk lower = On Track
Note on M4: Read-only preview of what the dashboard will show if Risk Level (column L) is left blank. This column is not read by the dashboard — it's just for your reference here in Excel.

## Monthly History
FTB Supply & Production — Monthly History
One row per site per month. Add a new row each month — never overwrite past months.
Month format: YYYY-MM (e.g. 2026-07). This feeds the dashboard's 6-month projection chart.
Site | Month | FTB Produced | Installed | Volume Produced m3 (Panels) | Volume Installed m3 | Manpower (Production) | Manpower (Installation) | Manhours (Production) | Manhours (Installation) | Target Installation | COCA | Target FTB Produced
Batulao Parkhomes | 2026-01 | 0 | 14 | 121.489 | 146.5 |  |  | 3176 | 525 | 60 | 14 | 60
Batulao Parkhomes | 2026-02 | 8 | 30 | 402.237 | 374.03 |  |  | 5112 | 760 | 60 | 102 | 60
Batulao Parkhomes | 2026-03 | 30 | 48 | 497.373 | 543.6 |  |  | 6429.87 | 923 | 60 | 81 | 60
Batulao Parkhomes | 2026-04 | 22 | 42 | 518.74 | 517.56 |  |  | 5454.94 | 631 | 60 | 82 | 60
Batulao Parkhomes | 2026-05 | 32 | 24 | 485.38 | 510.78 |  |  | 5103 | 657 | 60 | 20 | 60
Batulao Parkhomes | 2026-06 | 17 | 49 | 498.43 | 439.42 |  |  | 5314 | 828 | 60 | 70 | 60
Batulao Parkhomes | 2026-07 | 4 | 33 | 303.22 | 376.94 |  |  | 5252 | 797 | 60 | 4 | 60
Batulao Parkhomes | 2026-08 | 0 | 0
Batulao Parkhomes | 2026-09
Batulao Parkhomes | 2026-10
Batulao Parkhomes | 2026-11
Batulao Parkhomes | 2026-12
Calauan (Alora+Amani) | 2026-01 | 4 | 14 | 0 | 23.71 |  |  | 0 | 880 | 0 | 60 | 60
Calauan (Alora+Amani) | 2026-02 | 85 | 0 | 0 | 56.98 |  |  | 0 | 264 | 0 | 0 | 60
Calauan (Alora+Amani) | 2026-03 | 40 | 0 | 97.75 | 8.51 |  |  | 2640 | 664 | 30 | 0 | 60
Calauan (Alora+Amani) | 2026-04 | 24 | 84 | 689.28 | 644.01 |  |  | 8938 | 1250 | 40 | 72 | 60
Calauan (Alora+Amani) | 2026-05 | 12 | 90 | 567.3 | 755.36 |  |  | 9475 | 1224 | 60 | 102 | 60
Calauan (Alora+Amani) | 2026-06 | 0 | 64 | 672.15 | 506.18 |  |  | 10743 | 1119 | 70 | 44 | 60
Calauan (Alora+Amani) | 2026-07 | 0 | 96 | 527.36 | 672.01 |  |  | 12677 | 1074 | 70 | 28 | 60
Calauan (Alora+Amani) | 2026-08
Calauan (Alora+Amani) | 2026-09
Calauan (Alora+Amani) | 2026-10
Calauan (Alora+Amani) | 2026-11
Calauan (Alora+Amani) | 2026-12
Gentri | 2026-01 | 63 | 2 | 68.42 | 68.42 |  | 0 | 0 | 832 |  | 2
Gentri | 2026-02 | 20 | 32 | 625.59 | 625.59 |  | 0 | 0 | 760 |  | 32
Gentri | 2026-03 | 0 | 72 | 938.37 | 938.37 |  | 0 | 0 | 872 |  | 72
Gentri | 2026-04 | 12 | 70 | 478.43 | 478.43 |  | 0 | 0 | 1072 |  | 70
Gentri | 2026-05 | 22 | 39 | 561.22 | 561.22 |  | 0 | 0 | 1000 |  | 39
Gentri | 2026-06 | 15 | 17 | 226.26 | 226.26 |  | 0 | 0 | 520 |  | 17
Gentri | 2026-07 | 7 | 23 | 206.56 | 380.4 |  | 0 | 0 | 1024 |  | 20
Gentri | 2026-08
Gentri | 2026-09
Gentri | 2026-10
Gentri | 2026-11
Gentri | 2026-12
Naic | 2026-01 | 48 | 8 | 76.06 | 40.48 |  |  | 3998 | 456 |  | 44
Naic | 2026-02 | 114 | 62 | 516.85 | 500.23 |  |  | 11408 | 920 |  | 104
Naic | 2026-03 | 74 | 68 | 697.56 | 791.13 |  |  | 14799 | 1324 |  | 120
Naic | 2026-04 | 58 | 82 | 961.69 | 846.85 |  |  | 13705.16 | 1157 |  | 80
Naic | 2026-05 | 18 | 70 | 857.01 | 789.23 |  |  | 14154 | 1128 |  | 66
Naic | 2026-06 | 16 | 120 | 1074.94 | 1253.69 |  |  | 13364 | 1472 |  | 120
Naic | 2026-07 | 0 | 66 | 345.45 | 432.26 |  |  | 10965 | 680 |  | 52
Naic | 2026-08
Naic | 2026-09
Naic | 2026-10
Naic | 2026-11
Naic | 2026-12
The Cove Lipa | 2026-01 | 24 | 46 | 407.24 | 490.37 |  |  |  | 994 |  | 132
The Cove Lipa | 2026-02 | 44 | 42 | 415.08 | 434.61 |  |  |  | 1135 |  | 32
The Cove Lipa | 2026-03 | 52 | 56 | 513.78 | 509.37 |  |  |  | 1295 |  | 38
The Cove Lipa | 2026-04 | 74 | 72 | 627.25 | 642.85 |  |  |  | 1377 |  | 100
The Cove Lipa | 2026-05 | 46 | 48 | 569.3 | 696.62 |  |  |  | 1215 |  | 52
The Cove Lipa | 2026-06 | 50 | 74 | 600.34 | 658.17 |  |  |  | 1228 |  | 70
The Cove Lipa | 2026-07 | 0 | 36 | 640.51 | 571.03 |  |  |  | 1280 |  | 64
The Cove Lipa | 2026-08
The Cove Lipa | 2026-09
The Cove Lipa | 2026-10
The Cove Lipa | 2026-11
The Cove Lipa | 2026-12
Sights Bay | 2026-01 | 49 | 0 | [7 empty] | 57
Sights Bay | 2026-02 | 0 | 0 | [5 empty] | 0 |  | 19
Sights Bay | 2026-03 | 5 | 0 | [5 empty] | 0 |  | 12
Sights Bay | 2026-04 | 0 | 0 | [5 empty] | 0 |  | 32
Sights Bay | 2026-05 | 0 | 0 | 7.12 |  |  |  |  | 0 |  | 0
Sights Bay | 2026-06 | 0 | 28 | 200.81 | 193.7 |  |  |  | 768 |  | 0
Sights Bay | 2026-07 | 0 | 44 | 319.82 | 393.94 |  |  |  | 712 |  | 48
Sights Bay | 2026-08
Sights Bay | 2026-09
Sights Bay | 2026-10
Sights Bay | 2026-11
Sights Bay | 2026-12
Tayabas | 2026-01 | 0 | 0 | 0 |  |  |  | 5997 |  |  | 0
Tayabas | 2026-02 | 0 | 0 | 0 | 0 |  |  | 6352 |  |  | 0
Tayabas | 2026-03 | 14 | 0 | 3.29 | 0 |  |  | 7000 |  |  | 0
Tayabas | 2026-04 | 0 | 0 | 33.75 |  |  |  | 7254 |  |  | 0 | 14
Tayabas | 2026-05 | 0 | 14 | 35.32 | 141.95 |  |  | 6796 | 514 |  | 14
Tayabas | 2026-06 | 0 | 0 | 0 | 0 |  |  | 6531 |  |  | 19
Tayabas | 2026-07 | 0 | 0 | 0 | 0 |  |  | 7343 |  |  | 0
Tayabas | 2026-08
Tayabas | 2026-09
Tayabas | 2026-10
Tayabas | 2026-11
Tayabas | 2026-12
Batulao Impression | 2026-01 | 40
Batulao Impression | 2026-02 | 40 | 0
Batulao Impression | 2026-03 | 40 | 0
Batulao Impression | 2026-04 | 40 | 14 | 16.71 | 145.47 |  |  |  | 155
Batulao Impression | 2026-05 |  | 16 | 101.27 | 164.99 |  |  |  | 128
Batulao Impression | 2026-06 |  | 0 | 0
Batulao Impression | 2026-07 |  | 0 | 0
Batulao Impression | 2026-08
Batulao Impression | 2026-09
Batulao Impression | 2026-10
Batulao Impression | 2026-11
Batulao Impression | 2026-12
Note on B5: Use YYYY-MM format, e.g. 2026-07 for July 2026. This column is formatted as text so Excel won't auto-convert it into a date.
Note on E5: Cubic meters of panels produced THIS MONTH by PCS (not a running total).
Note on I5: Production-crew manhours THIS MONTH. Kept separate from installation manhours.
Note on K5: Planned/budgeted installation for that month.
Note on M5: Planned/forecast FTB availability from the client (Phirst Park Homes) for that month. Compare against actual FTB Produced to catch client-side delivery delays early.

## Annual History
Annual History — Reference Only (2021–2025)
Historical reference before monthly tracking began. Not read by the dashboard — Monthly History (2026+) is what feeds the live projection.
Site | Year | FTB Produced | Target Installation | Actual Installation | RFIA COCA | COCA
Batulao Parkhomes | 2021 | 104 |  | 104 |  | 42
Batulao Parkhomes | 2022 | 585 |  | 585 |  | 637
Batulao Parkhomes | 2023 | 291 |  | 291 |  | 224
Batulao Parkhomes | 2024 | 296 |  | 296 |  | 353
Batulao Parkhomes | 2025 | 450 |  | 308 |  | 56
Calauan (Alora+Amani) | 2025 | 356 |  | 68 |  | 10
Gentri | 2023 | 469 |  | 121 |  | 74
Gentri | 2024 | 356 |  | 596 |  | 572
Gentri | 2025 | 415 |  | 315 |  | 173
Naic | 2023 | 117 |  | 0 |  | 0
Naic | 2024 | 304 |  | 276 |  | 186
Naic | 2025 | 469 |  | 306 |  | 254
The Cove Lipa | 2025 | 554 |  | 230 |  | 128
Sights Bay | 2023 | 402 |  | 86 |  | 74
Sights Bay | 2024 | 980 |  | 784 |  | 612
Sights Bay | 2025 | 608 |  | 870 |  | 934
Tayabas | 2023 | 446 |  | 286 |  | 272
Tayabas | 2024 | 800 |  | 566 |  | 548
Tayabas | 2025 | 190 |  | 408 |  | 387
Batulao Impression | 2025 | 24
Note on D4: Planned/budgeted installation for that year.
Note on F4: Request for Inspection/Acceptance — the stage before final COCA clearance.